## All Projects 2
(Do Not Modify) Project | (Do Not Modify) Row Checksum | (Do Not Modify) Modified On | Project ID | Name | Portfolio | Project Status | Overall Health | Budget Health | Schedule Health | Resources Health | Scope Health | IT Department | CPMS Project Number | Current Stage Name | IT PM Requested | Project Manager | Requestor | Business Sponsor / Champion | Locations Impacted | Start Date | Finish Date | Created On | % Complete | Active Changes | Active Issues | Active Risks | Actual CAPEX | Actual CAPEX (Base) | Actual OPEX | Actual OPEX (Base)
93227cf1-fad9-f011-8544-000d3a356313 | I5mxJXySXHjHX3GBAGxzQzWo2AGR2/l3oGyzb7CRMZe8FWT0/NEdqOKDZGMHCPR0LLCa7zOT4kT4ljzkfKNHxg== | 2026-02-26 19:13 | 1527 | Nakisa replacement | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Jeanie Thompson | Global | 2025-12-15 17:00 | 2025-12-15 17:00 | 2025-12-15 21:14 | 0 | 0 | 0 | 0
1ff85501-9989-f011-b4cb-000d3a356313 | 89BlF6V3B1O/wbv2fAXbbo2UswWMreHvNcepZ3n/bj3UbEACnV9V75Uf7ag0yMIX+ghqxfLP8WUzToUITaSD9A== | 2025-10-30 14:02 | 1454 | Rio 2026 | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Kathy Seifarth | Kathy Seifarth | Brazil | 2026-01-01 06:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
35c65d1d-f6d9-f011-8544-00224802cf58 | 5w0LttnM1m0Qpg90K7wUXmvlHxvOZUT7Av019IMXaP0HI6EI+J4heEZ9wwV5SLznVBkAXAz/f4PPQQ3oziLaxQ== | 2026-04-01 14:16 | 1525 | SAP Document Compliance_Germany and Italy | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Rosanne Richter | Germany and Italy | 2025-12-15 17:00 | 2025-12-15 17:00 | 2025-12-15 20:39 | 0 | 0 | 0 | 0
e953ffe5-9889-f011-b4cb-00224802cf58 | lOu0Kb+hJI5bwjclrKQvdNoRB3kA3VuZp/sIkVGKeghEJoGu85feULswkaWRR3GDnxeYEOfLRyCS5WN0v+0nqA== | 2026-02-26 19:08 | 1414 | Implement EAM Extension for Plant Maintenance Objects (FLOC, Equipment, MBOM) | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Allyson Taylor | Kathy Seifarth | All Chemicals manufacturing/maintenance locations | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
aaa018f2-9889-f011-b4cb-00224802cf58 | ea6Pa3edsXc01JvK1rVhMEFFxD7mRz021juTAYeqD3o2/OAz6QS+ehy+soMxjX4isIh6DRepv362mPGv2LLJ3g== | 2026-02-26 19:09 | 1429 | Migration to SAP Business Data Cloud (BDC) | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Kathy Seifarth | Kathy Seifarth | Global | 2025-09-04 16:00 | 2025-09-04 16:00 | 2025-09-04 14:11 |  | 0 | 0 | 0
823c8230-2601-f111-8406-00224805f204 | loPPTOo8aksFaLnRZG6TYVg9ZJtO8zitPoJuSuE53HCRpMB9pA+Hj2kONW9ZQkMir8g5jgGSPSIy280Pfeskgg== | 2026-03-10 14:24 | 1532 | Bourque Logistics | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Kathy Seifarth | Global | 2026-02-03 17:00 | 2026-02-03 17:00 | 2026-02-03 17:32 | 0 | 0 | 0 | 0
c9a3ac40-01da-f011-8544-6045bd060015 | iM6cKmGsPFw2sE8IlooYNkHHyZJ0+qrsb241DEJ9HO1cy6+CihskSKHaBrvcNjgd3+h5SC/rIZIhHy8B2Y7UNQ== | 2025-12-15 22:02 | 1528 | AES32 Time Management Module | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Matthew Stewart | Freeport, Plaq | 2025-12-15 17:00 | 2025-12-15 17:00 | 2025-12-15 21:59 | 0 | 0 | 0 | 0
03a36646-f6d9-f011-8544-6045bd0857df | ddTivGLNYAxX/LgPQm9lMbO6zWfW04JTfsqkL3OCGDBgYITDjMDd0qIpyd4ed/wSqC4Eo/hef7Sr8V+ixMA4tQ== | 2026-02-26 19:10 | 1526 | Project SOPrano | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Alex Weir | Global | 2025-12-15 17:00 | 2025-12-15 17:00 | 2025-12-15 20:40 | 0 | 0 | 0 | 0
31b40e0c-2601-f111-8406-7ced8d3be8bf | YFY31MS6+c59F9EVJMBtUDR8Iots9HC7Mg+DPYP0dlWJR3LXptg9JcuLLhD/QWXOZkl7P57lYbdu4zFkMmxzug== | 2026-02-25 18:09 | 1531 | GTS Upgrade | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Kathy Seifarth | Global | 2026-02-03 17:00 | 2026-02-03 17:00 | 2026-02-03 17:31 | 0 | 0 | 0 | 0
81a018f2-9889-f011-b4cb-00224802cf58 | lcCZS5Amp5HG2sw2MCmq2WvgZuxOHZmPiJVDUfP54IPsjkNH7IG7bJ7eXE3ehYN0IvMiTC5se/aGYXFhaFEZtg== | 2026-02-26 13:25 | 1425 | Migration from Celonis to Signavio | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Ent Solutions | X.CLA.000050 | Execution | No | Brian Courtney | Kathy Seifarth | Kathy Seifarth | Global | 2025-09-04 16:00 | 2026-04-10 09:00 | 2025-09-04 14:11 |  | 0 | 0 | 0
5c4c3dca-f98f-ef11-ac21-000d3a3161c7 | ZH1PFbvZ3jRuz9hmtSinIIgBAe/epO6U+OZd4DBB+4yhcEoAFyuX1PVo9nWG5V1ciwFOQMfAsLDenCU/KVq/iw== | 2026-03-31 17:56 | 1334 | Network Access Control (NAC) ClearPass | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Margaret Broder | Dennis Allen | Global | 2024-10-21 16:00 | 2024-10-21 16:00 | 2024-10-21 22:14 |  | 0 | 0 | 0
40995dfb-9889-f011-b4cb-000d3a356313 | iB7Mmfwia1oL/lf9gLKcJFxnrM37gAwpoEjavPeB5kp+MbBMLMEexryHUEn9UauBNdmcAAifMJej1l3CF9AQHw== | 2026-02-26 19:14 | 1448 | Netskope - China POP | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Steven Beasley | Dennis Allen | China | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
4e995dfb-9889-f011-b4cb-000d3a356313 | HWGIsIAAe4S+uOkXVqIhQVNkrYrVRFgoEPd/YuUSeFwr4KnHfQ+k/5rYMsEEJU4m3xWvtP7dHorOayLcF6smTw== | 2026-04-01 15:37 | 1450 | OT Cyber Security Awareness Content | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Intake Gate 2 | No | Md Uddin | Nathan Faith | Dennis Allen | All | 2025-09-04 16:00 | 2025-09-04 16:00 | 2025-09-04 14:11 |  | 0 | 0 | 0
ca0ed10d-9989-f011-b4cb-000d3a356313 | bD0fJzowBg9GaTS4w0adfrXPjqSoiwDq29nfrSTKKOmHbvkSFPmQlBZc5hnHHmNOrdGOjEpylhNKH9OgG6iWCw== | 2025-10-06 15:26 | 1482 | Cyber Security Awareness Training Platform | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nathan Faith | Dennis Allen | ALL | 2025-09-04 16:00 |  | 2025-09-04 14:12 |  | 0 | 0 | 0
6e163ecd-f98f-ef11-ac21-000d3a3ae441 | AvEj9OhoBmAaPChgwyBEWFoJo2Bmgc+1hwkBr/p9vcQLCJIGbPsBeYMJLWXnEwCH3nCsWvO6R+/6GOVl+7IUnw== | 2024-10-22 02:27 | 1340 | Application Development Discovery - Secure Development | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Margaret Broder | Dennis Allen | Global | 2024-10-21 16:00 |  | 2024-10-21 22:14 |  | 0 | 0 | 0
bc639595-0e87-ef11-ac21-002248080eef | BrR35FNLqc7KJB/5cp7nQQ9cY9KgLhfp5yCfFgOzfWAJXtExlCHa+E4XmPWLQwFO/5Jvysi4WedixUXIo+7N2A== | 2025-10-13 16:28 | 1330 | CyberSixGill - Dark Web Monitoring | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS | x.cla.000029 | Intake Gate 2 | No | Steven Beasley | Steven Beasley | Dennis Allen | No direct impact to users, will provide server for Senior and Exec Management | 2024-10-10 16:00 | 2024-10-10 16:00 | 2024-10-10 13:50 | 0 | 0 | 0 | 0
0bf3a5bb-ebf0-40c0-9261-d89f4cb5acaf | yym0ZLusZsj2guXifkcE0TpvmDgS6lOo2MQ6raQz9d3DSK7rPWgQwvrE6uXDnZAnc9NMRb9egeydGtFVO/CiKQ== | 2026-02-26 19:09 | 1495 | CUI Boundary Diagrams LCAP (HOLD) | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Dennis Allen | David Kellar | Winchester locations | 2026-06-01 | 2026-12-31 09:00 | 2025-09-10 17:43 |  | 0 | 0 | 0
c0359777-f40b-474b-b12a-f2ea54e0ac3e | tG6/ifEZ7GhPI4oqyVnkikU5yNI7mbhXQYSLZ4RBOM3PCnalK7D+BssJiaFVoWrgd+b2ToY0KGqlh9s6gkd/lA== | 2025-12-05 19:42 | 1496 | (HOLD) CMMC 2.5: Security Protection Assets (SPAs) | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Intake Gate 2 |  | Darlene Schumer | Dennis Allen | David Kellar | Winchester locations | 2025-10-06 | 2026-03-31 09:00 | 2025-09-10 18:22 |  | 0 | 0 | 0
734c3dca-f98f-ef11-ac21-000d3a3161c7 | IsiiMzeWa1fc4YlkkpKAc5TGlntMqzo1pCcoi7A3JvT8f6V7Mmo+RpTMdtTnl21WFm3DTCtOZgigvrsJJGpqeg== | 2026-03-27 13:28 | 1338 | End-of-Life Firewall Replacements | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS | I.CLA.000041 | Execution | Yes | Bob Cassout | Margaret Broder | Dennis Allen | Global | 2024-10-21 16:00 | 2026-06-30 17:00 | 2024-10-21 22:14 | 0.56 | 0 | 0 | 0 | 140379 | 140379 | 39235 | 39235
2a995dfb-9889-f011-b4cb-000d3a356313 | aHZKMRCChzwhqSg/4q+GKMtIbPDiI53RC0oBgWAqMEJA9iJy5GSnnf5tr2KHPdGiWyufJdt8KMGG3A+ebYq4yw== | 2026-03-27 13:36 | 1447 | NIS2 Compliance Assessment and Readiness | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS | X.CLA.000049 | Execution | Yes | Bob Cassout | Nathan Faith | Dennis Allen | Chemical HQ, Germany, Italy | 2025-12-01 06:00 | 2026-06-30 09:00 | 2025-09-04 14:11 | 0.24 | 0 | 0 | 0 |  |  | 63333 | 63333
2ef85501-9989-f011-b4cb-000d3a356313 | GCbp3csrMtn3zo9MiFFGvufouhK4YjdRT3kKbcEx+sjS4UKB37UqtPC7VrVOYydBXoGXByOFi9cvb6Z+/C1HUQ== | 2026-03-27 13:30 | 1455 | Onapsis Defend Implementation | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS | N/A | Execution | Yes | Bob Cassout | Nathan Faith | Dennis Allen | Winchester and Chemicals | 2026-01-01 06:00 | 2026-07-03 09:00 | 2025-09-04 14:11 |  | 0 | 0 | 0 |  |  | 888 | 888
a64610f2-d5a2-f011-bbd2-000d3a59edd5 | w33QT+9gXeMsVbVeQU4oavIGvzbEacdBGHk0w0kEXX0Gz/hUJ//+7P7n2Jn/84TcMYuBIBBgc92AXihO555IzA== | 2026-03-23 13:07 | 1503 | SentinelOne Cloud Security POC | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Execution | No | Bob Cassout | Steven Beasley | Dennis Allen | Global (Not Germany for now) | 2025-11-04 06:00 | 2025-11-04 06:00 | 2025-10-06 17:01 | 0 | 0 | 0 | 0
7d35f9ab-1a21-4ace-b654-10756933effe | 6YMCg/WRZpCAGTYpoiPolVu6nYwyk47iQU+/pv3wg36Xix5mZvkV7Ahp9p39mEiZyXTh6xY7+8189QCCMz1I5w== | 2026-03-25 16:44 | 1491 | CMMC: 5.1: Portable Storage Governance and Malware Protection | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Execution | Yes | Bob Cassout | Dennis Allen | David Kellar | Winchester locations | 2025-10-15 09:00 | 2026-04-30 17:00 | 2025-09-10 17:26 | 0.84 | 0 | 0 | 0
a6857c61-30b5-ee11-a569-6045bd03b718 | Bmq5GwwwaTSlymstHYlXA8s9UFn8lF9pN5YKsHSRA3jU2GC8ji1xEOEHlJZj23ZXxywI7JM4uv9fEZPBt08+8w== | 2026-03-23 12:57 | 1248 | Armis OT Collector Deployment | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS | TBD | Execution | No | Bob Cassout | Michael Ehlers | Dennis Allen | Plant locations | 2025-01-06 09:00 | 2026-12-03 17:00 | 2024-01-17 12:03 | 0 | 0 | 0 | 0
8e2db857-19a5-f011-bbd3-6045bd060015 | oaWK2t7zPIvDZMKZK4gDe8xeYTj9WIjpMQpzJ40mY76b4+E9mspJ3ADvIrN1XOTzF8azQ3KidiXjGHNG82CfDg== | 2026-03-23 13:29 | 1512 | KnowBe4 | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Execution | No | Bob Cassout | Jason Vogel | Dennis Allen | All | 2025-12-01 06:00 | 2026-03-31 09:00 | 2025-10-09 14:08 | 0 | 0 | 0 | 0
a58666e8-26d1-f011-bbd3-6045bd060015 | PCFYStMXbbtRkYfUe11WWZhc5q3EC9Lc8tcNpb+WlpeegKwUtI+YaAE0GjvXpLd6/MXQ9HGSZpKLHoKAkCtDkw== | 2026-03-25 13:40 | 1516 | Archer NIS2 Tracking Implementation | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Execution | No | Bob Cassout | Adam Barletter | Dennis Allen | Chemicals | 2025-12-04 17:00 | 2026-05-28 09:00 | 2025-12-04 15:36 | 0.51 | 0 | 0 | 0
48a68166-317a-4f1e-8ca5-72f5070efb98 | 7WPzWhl9a0PJ8PEtr0dPML+G3sXp6V1XpOmZjLNTNUPoFaDvi/p3vG4CanA1BunSx21gOS5matyh4qqL43es7g== | 2026-03-30 13:34 | 1504 | OT Remote Access Solution | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS | X.CLA.000048 | Execution | Yes | Bob Cassout | Steven Beasley | Dennis Allen | US | 2025-11-03 | 2026-05-29 17:00 | 2025-10-07 18:45 | 0.21 | 0 | 0 | 0 |  |  | 445 | 445
1fc5e67c-51fc-4ed3-a7d0-7466c6bc1b42 | Z7ihOOdmWPis5oxxB09ODynkT93EwaXCl1zDvDSc1LOEjV978jzmiB+nNG1YqCy6NuSbBdLmNGl/Bn2OS4vbwQ== | 2025-11-05 23:32 | 1120 | CMMC 7.1: EALT Purdue Model Implementation | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS |  | Execution | No | Bob Cassout | Steven Beasley | Rory Lynch | East Alton | 2024-06-03 05:00 | 2025-12-19 14:00 | 2023-02-03 21:19 |  | 0 | 0 | 0
19054702-8031-47c8-af22-f3686c8800da | 3Uv3dTBEZOFCdBsv0NuSMNCU3MJFZq00R8yNh5PWxy6DLhuA384KRrAO27w0kBerRzl00QGEJ9m10atA6MAj/Q== | 2025-12-01 17:27 | 1265 | CMMC Certification Readiness | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | GIS | 240068 | Execution | No | Darlene Schumer | Margaret Broder | Dennis Allen | Winchester locations | 2024-10-07 05:00 | 2026-05-12 17:00 | 2024-02-14 21:42 | 0.93 | 0 | 0 | 0
a4314354-b923-f111-8341-000d3a36aadd | CvNKwKonNVy8xByy7bQOIUPzZpwUgGRifNfxs0qqr52keOYB9w/I2lqrfXl1QBlOYotXaes+JW+wFjLX5Sd/5Q== | 2026-03-19 21:09 | 1536 | UKG Clock Replacements - Chemical Locations |  | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | HR |  | Intake Gate 2 | No | Carolyn Henderson | Carolyn Henderson | Carolyn Henderson | Chemical Locations | 2026-03-19 16:00 | 2026-03-19 16:00 | 2026-03-19 17:31 | 0 | 0 | 0 | 0
1c4efc88-2d76-4fb4-8c27-c15417fa4798 | lE24z0ngcxewtDxRuphUc+1fL/lrdst/6bhnlFwJi6LZWthFNoSrN3QBA+1pQ1IN2T1lNH6VwTimL6E7LrIgwg== | 2025-02-20 20:35 | 1151 | Becancour Kronos Implementation | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | HR |  | Intake Gate 2 | No | Carolyn Henderson | Jonathan Brewer | Carolyn Henderson | Becancour | 2023-02-15 09:00 | 2023-02-15 09:00 | 2023-02-15 21:04 |  | 0 | 0 | 0
74a84624-443e-ef11-8409-00224808f30b | RPNTtemutSNDUGvc1E1G5Ls3En0OFRn0Ioy6rcdboz4DpebV11/seKjNARg5C1HUNx4gVwY0pNsVIudCkqa8RQ== | 2026-03-31 18:45 | 1311 | HCM Replacement | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | HR | I.CLA.000032 | Execution | No | Brian Courtney | Carolyn Henderson | Valerie Peters | Global | 2025-01-06 06:00 | 2027-09-30 09:00 | 2024-07-09 22:40 | 0.61 | 0 | 0 | 0
091aabda-bf7f-4452-912a-1413ba519d60 | B09XvBAOFAf31sHqAxP4oZTf9q1G8nw4J1eoc5fODWKpMnT1WK80BXPB5+6InvEMYCYGQdZWob7CXeT8O07Iag== | 2026-03-20 13:37 | 1505 | UKG Dimensions Germany | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | HR | I.STA.000003 | Execution | No | Brian Courtney | Carolyn Henderson | Stephanie Brandenberger | Stade, Rheinmuenster, Baltringen | 2025-10-07 14:00 | 2026-10-01 17:00 | 2025-10-07 22:28 |  | 0 | 0 | 0
b1580cc6-04d0-4e9a-a171-7e69ba662b14 | zZqge9jrZEfr/6BDohjVUYj28p//qWRkP4IiOGRc9dmIFc+IqdE3TNMh1aUm2iTfIN5J2aq7/cvFtmCfJ+X9lw== | 2026-03-30 21:05 | 1492 | CMMC 6.1: IAM/IGA Implementation | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | HR |  | Execution | Yes | Seth Aldrich | Jeffrey Miller | David Kellar | Winchester locations | 2025-09-10 09:00 | 2026-06-30 17:00 | 2025-09-10 17:33 | 0.87 | 0 | 0 | 0
51c23cd0-f98f-ef11-ac21-000d3a3161c7 | vE0HFqsBa+11nG00YrQamfsYE1D1dkvS9J1ByQTZLdZdWaYlZdyxHJml3Rb3c5pkMlW9mldl/x8Cf1TKU85AHg== | 2026-01-28 20:19 | 1351 | ESX Server Upgrades | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Andy Pilgrim | Mike Somers | North America;EMEAI | 2024-10-21 16:00 | 2024-10-21 16:00 | 2024-10-21 22:14 |  | 0 | 0 | 0
3d4fa2f2-c602-f111-8406-002248097567 | urwc7l3t+xCRDCrS7QkDcqS78Xh1JTyERVG3zSZLhFwCJeDxiIKaQTPmU1OSg4EcFQN6AtVT+a5E4+F9ULFUMQ== | 2026-02-26 19:11 | 1533 | Unified Communications Discovery Project |  | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O |  | Intake Gate 2 | Yes | Michael Boone | Michael Boone | Mike Somers | East ALT, Clayton , Houston & Oxford | 2026-02-05 17:00 | 2026-02-05 17:00 | 2026-02-05 19:15 | 0 | 0 | 0 | 0
9d5f535e-cd20-454e-904b-51795995c2f5 | 3ParCuipXM9LdsP7QH/3jB99Nar5qFeHlr/dWkvJ94MitVNGl9bHI5uX7SqwfztaMEH55kWognFqP9LkVs54aQ== | 2025-10-06 15:28 | 1494 | Separate IT OT network at Lake City | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O |  | Intake Gate 2 | Yes | Mike Somers | Mike Somers | David Kellar |  | 2026-06-01 | 2026-12-31 09:00 | 2025-09-10 17:41 |  | 0 | 0 | 0
13d005de-f695-4763-96f3-c2f214c6440d | pTh10yI5hSGBYf4TKYgtkXtnME4Mt3wAgvARB/+gETMujpaI1wbUy5oMO6K1tcipoNs96Mrx1ieZHslaBmpDTA== | 2026-02-25 18:16 | 1497 | NAC Implementation Strategy LCAAP (HOLD) |  | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Mike Somers | David Kellar | Winchester locations | 2026-06-01 | 2026-12-31 09:00 | 2025-09-10 19:13 |  | 0 | 0 | 0
24c23cd0-f98f-ef11-ac21-000d3a3161c7 | uuOJgWYukuYIKnvc6RiZ/Ovc+9LR881uknxTCH7YMCYO4zWfsPJKKGG2UIN5Ie23fwz2N3w3Yljuuw9D70eeyg== | 2026-03-31 13:01 | 1345 | Remote Access Solution Replacement | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O |  | Execution | No | Jeff Dahl | Ajay Vedre | Mike Somers | Global | 2025-12-01 06:00 | 2026-12-30 09:00 | 2024-10-21 22:14 |  | 0 | 0 | 0
7539fa28-b1a0-4335-9930-07c6e2ebe56e | UYCob2pcAGAmHDR0ExiJvYMB14SIkfumHBwrovT1+Yn1xn9tQ1N3LBrjYBCPgKAIIsgc33NuBoRbzzxfm+evNg== | 2026-03-30 13:27 | 1132 | SDWAN deployment | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O | X.CLA.000008 | Execution | Yes | Jeff Dahl | Michael Boone | Mike Somers |  | 2023-02-03 09:00 | 2026-12-18 17:00 | 2023-02-03 22:23 | 0.55 | 0 | 0 | 0 | 0 | 0 | 68767 | 68767
9c6b10c7-a371-421f-a089-0863dd0a2014 | s4mTMhgNpRnZ42TEbTCsm5Okl5lASXFeZJ6EkLnbAoaItCXb3FNceWvvVNNe4k4hi0OEx3cSPrHDwpwHG7fJXQ== | 2026-03-30 13:16 | 1380 | 2026 Server Room Power supply requirements | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O | X.CLA.000051 | Execution | No | Jeff Dahl | Ajay Vedre | Anthony D'Amato | EALT | 2025-04-01 | 2026-12-17 17:00 | 2025-03-21 14:43 | 0.1 | 0 | 0 | 0 |  |  | 206 | 206
3e2e271d-efb3-4013-9f8e-53ae120cde2c | sjdaQ7HDPJt/EESgIYADaKa1B5kiupRXhGCluLZRCQ7s6x5LvmZiacuYUzjfJ/hHj8ie0qKpE1RgPrlQBNncCg== | 2026-03-30 13:30 | 1129 | Network Switch Replacement - Cisco Audit | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O | X.CLA.000027 | Execution | Yes | Jeff Dahl | Michael Boone | Mike Somers | OXFD SHAN ZHAN ROBE | 2023-02-03 09:00 | 2026-12-18 17:00 | 2023-02-03 22:17 | 0.7 | 0 | 0 | 0 | 0 | 0 | 47697 | 47697
f1b46ff1-96d9-f011-8544-6045bd060015 | R9ZL/waYhqtW1XhDs7a+G9vlNwfCb8kjSIiGowKiZqJeptVQI+82zr0ZGs9gK5pE28X6/ESw3Fg48cs4wPPAGA== | 2026-03-23 13:17 | 1519 | Migration InfoBlox NIOS to BloxOne DDI Solution. | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O |  | Execution | Yes | Jeff Dahl | Michael Boone | Mike Somers | Augusta, Baltringen, Bencancour, Charleston, Freeport Plan A& B, Henderson, Houston Katy, Lemont, McIntosh, Nigara Falls, Oyster Creek, Pisticci, Plaquemine, Rheinmunster, Roberta, Russellville, St. Gabriel and Stade DE. | 2025-12-15 17:00 | 2026-06-30 17:00 | 2025-12-15 09:18 | 0 | 0 | 0 | 0
21e4098c-75ea-f011-8544-6045bd060015 | 4uh/ZdQq7/Sc4wKSJJ0EL3BPRbnip6Mkmp8L361fDmt3aVXTtJ3/SG8X/6426M9gvNwJyPP1pbC++IfHpmOj4w== | 2026-03-30 13:29 | 1529 | Skyline | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O |  | Execution | Yes | Jeff Dahl | William Smith | Anthony D'Amato | All Olin locations | 2026-03-02 06:00 | 2027-04-02 09:00 | 2026-01-05 20:32 | 0.02 | 0 | 0 | 0
6f424ee3-06de-4fcb-a823-b1e0ec12ee77 | muNE9OO49MNRH3tCvUCM9puw5xuSioOVpK67InjMT9xQxWRHMiIWUhotQ6jglLyE+6FQo1/OjK5JiU3Z4lB0sg== | 2026-03-30 13:22 | 1383 | CMMC 4.1: Network Remediation | CMMC Remediation Portfolio | Active | (2) At Risk | (1) On Track | (2) At Risk | (1) On Track | (2) At Risk | I&O | 240068 | Execution | No | Jeff Dahl | Michael Boone | David Kellar | Winchester locations | 2025-04-11 09:00 | 2026-06-26 17:00 | 2025-04-11 21:11 | 0.25 | 0 | 2 | 3
ac7558a3-020b-4001-8499-c2897d5db5f6 | R1XcjaOAa875ZBz8cvMFai2gHGgLS4Wl7hyxLbDIbHgMZjJxorKRFAEQvsML+tFF7X/0IZ7dlmJsCZDJL3MXEg== | 2026-03-23 19:05 | 1500 | EALT/OXFD Azure Gov Migration & End-of-Service Hardware Refresh | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O |  | Execution | No | Brian Courtney | Mike Somers | David Kellar |  | 2025-07-01 | 2025-12-01 09:00 | 2025-09-15 17:03 |  | 0 | 0 | 0
0c674f9c-b327-4896-a222-cc8cc9438cfc | xUKszpvxwMUvNHDr8OLvo5Bjj7Z2Yoq/oAmMdE/z53D3A7wibHjR57o+ZX8b19/ZpJ0IIQZH5AcxkDMy95A1/w== | 2026-03-30 13:33 | 1126 | Telephone Replacement | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O | I.CLA.000040 | Execution | Yes | Jeff Dahl | Michael Boone | Mike Somers | MCIN, PLAQ, PLAQC, LEMT, DNGV, RUSS, CHAS, FMRO, FPLJ, OYST, FREEA, FREEB, MILA, PIST, TERN, RHEI | 2023-02-03 09:00 | 2026-12-18 17:00 | 2023-02-03 22:12 | 0.88 | 0 | 1 | 0 | 199043 | 199043 | 12938 | 12938
f968c055-b42c-454b-a8ed-edac8d57b948 | VqNBGgL77hJv+Sa6oTsiYdA4ndp+cVhJoXOvdIPiuVa4JSPCKxlSuXHXp//brvJVV+sO0A6E/7J7as+orymx4g== | 2026-03-27 21:01 | 1499 | CMMC 3.1 & 8.1: Application OS Upgrade Remediation (Blueprint 360) | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | I&O |  | Execution | Yes | Seth Aldrich | Mike Somers | David Kellar | Winchester locations | 2025-09-22 | 2026-04-17 17:00 | 2025-09-15 16:57 | 0.81 | 0 | 0 | 0
e20c94d6-a45a-4ca6-b840-ee7f5950595a | meThb2jh8RvUkUrQiVZ1MlzW/b3+ZgCFlwEV/LM++1O6WroI0hUWJmXoZv2PbnIXYDrPTwD5Ic0h1Xwwe6oMxA== | 2026-03-30 19:40 | 1386 | CMMC 2.8: Olinammo.com SN to FedRamp | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (2) At Risk | (1) On Track | (1) On Track | I&O | 240068 | Execution | No | Michelle Kissell | Mike Somers | David Kellar | LCAAP | 2025-04-30 09:00 | 2026-02-27 17:00 | 2025-04-22 15:43 | 0.88 | 0 | 0 | 1
1c546765-4293-f011-b4cc-000d3a58fbd0 | 671PThH7FWx3cx3iA22Jm5ZCKfRHmDvuS50ZF4BYt4GElbz0EFTp3o6Ps66854/Ce/y7H6W//HBnU/zWbK8o3A== | 2026-03-27 20:44 | 1501 | IT Financial Integration | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | ITSBO |  | Execution | Yes | Seth Aldrich | Darlene Schumer | Greg Rutherford | Corporate IT. IT Procurement | 2025-10-13 | 2026-05-29 17:00 | 2025-09-16 21:17 | 0.49 | 0 | 0 | 0
5a8cdaf1-beba-401a-bc8e-e3bbda4af62c | TNxiUCFBULTOlS8PBfatuga7uJGCqLZQ/mo70Qn9W7iUW3sh/wAttNhn4Efw8xJTq8jQkOlSU7bKAfgaB1BLtA== | 2026-03-30 21:11 | 1366 | CMMC 3.1 & 8.1: Blueprint 360 (Config Mgmt/Risk Assessment) | CMMC Remediation Portfolio | Active | (2) At Risk | (1) On Track | (2) At Risk | (2) At Risk | (1) On Track | ITSBO |  | Execution | Yes | Seth Aldrich | Darlene Schumer | Greg Rutherford | Corporate | 2025-01-13 06:00 | 2026-11-27 17:00 | 2024-11-18 19:09 | 0.95 | 0 | 1 | 2
1cc23cd0-f98f-ef11-ac21-000d3a3161c7 | VqqtCyOGUCprV1rKJe3Gon1ZTZWb+eEB9brVP4EJWUFf/tXzRy4bsfPC4TqGFLhj3lA1fXHHeKwv9u+rQsRRUg== | 2024-10-22 02:33 | 1344 | Documentum High Availability | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Jeff Brantley | Global | 2024-10-21 16:00 |  | 2024-10-21 22:14 |  | 0 | 0 | 0
1dc23cd0-f98f-ef11-ac21-000d3a3161c7 | T/egX05VrD7zjGKQW5t7KXVutTxwz3fYFuWIyHtjXiGPhWN/2M1efUlgY5oEQb7xPuZBeCU+4LIr2mLHYwSSaQ== | 2024-10-22 02:33 | 1343 | Update dashboards, reports, and alerts related to LIMS systems upgrades | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Jeff Brantley | Global | 2024-10-21 16:00 |  | 2024-10-21 22:14 |  | 0 | 0 | 0
25c23cd0-f98f-ef11-ac21-000d3a3161c7 | S7RZJIwgmnKNKh56qiPosKIr6zF6aAZTZkjJU4wnOzvGs4tjM1tF2rppDQIsPNvVGu1ijAW/kVEj+p+uCKwFxA== | 2024-10-22 02:33 | 1346 | Retire WebTop from Documentum Systems | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Jeff Brantley | North America | 2024-10-21 16:00 |  | 2024-10-21 22:14 |  | 0 | 0 | 0
4fc23cd0-f98f-ef11-ac21-000d3a3161c7 | 2OsFGo+GFobEbvQq+gtfgThNo16dFbCUInshx3fANsDZP5uUH5fMCjYrRzOmhOKHcP1XgLVStcXJr30jmLuAjA== | 2025-01-16 06:09 | 1350 | Upgrade IP21 application to latest version | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Jeff Brantley | Global; | 2024-10-21 16:00 | 2024-10-21 16:00 | 2024-10-21 22:14 |  | 0 | 0 | 0
6cc23cd0-f98f-ef11-ac21-000d3a3161c7 | JJ4UpfTvAVwRwUOqB3ALOxiXUSaOQaALHnwrK9flXblf6BuJRcObEivEsexn3NTrQsDl2SgDIb3ui6AT+QQYqQ== | 2024-10-22 02:33 | 1354 | Documentum Cloud Modernization | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Jeff Brantley | Global | 2024-10-21 16:00 |  | 2024-10-21 22:14 |  | 0 | 0 | 0
9ec23cd0-f98f-ef11-ac21-000d3a3161c7 | D8XL/zcGmcT7sPIdGJbWy9iYFZ+oJyTq9LAvpZmLHd1CBaFshLDUdDGRDwQV7Ch3cLaIioMFlUuQVFSH9/xMyA== | 2024-10-22 02:34 | 1359 | Documentum OlinWC Software Enhancements | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Jeff Brantley | Global | 2024-10-21 16:00 |  | 2024-10-21 22:14 |  | 0 | 0 | 0
1489ddee-9889-f011-b4cb-000d3a356313 | 9k8qMrYksEmW8Ya2eC5gOO2n2JyK15N+czA3V0erDS/Lrol3m5xbO14HbeciWEkFrpQzXdvVNJmbExBfoyoaYg== | 2026-02-25 18:13 | 1418 | GPI Workstation upgrades |  | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Chris Culberson | Global | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
52f85501-9989-f011-b4cb-000d3a356313 | jnrNmO4ZRL5yE0xHCsELi+Owl2avi9wIJdV7yS73OykZf4OiLkccXywgzsl66MtJRbgHp9ojhPrCqZ6fDbHr4w== | 2026-02-26 19:13 | 1459 | Move PCMS from on-prem to SaaS | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Chris Culberson | Global | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
91f85501-9989-f011-b4cb-000d3a356313 | 1MUe+qrcmzTt/hsDWnT+KaAXKw7ebsFXVCGsv9kO5h8ihwsqqu2n/RiPKFZxqDG9/1rznVheUzRQheqTf7Uagw== | 2025-10-13 14:11 | 1471 | ShiftConnector GO Implementation | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Felim Larkin | Bruce Raiff | Global | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
a5163ecd-f98f-ef11-ac21-000d3a3ae441 | R/UFkAAz8xlsJdhc1I6wglF+LO9aqH+qJCoQ0wcxxoCoqcLSRmuDUU4FxWvFSueQjZugbIOebOi3nHKrMrjKuw== | 2024-10-22 02:34 | 1356 | Upgrade the M&E IT SolarWinds environment | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Jeff Brantley | Global | 2024-10-21 16:00 |  | 2024-10-21 22:14 |  | 0 | 0 | 0
3cac53f8-9889-f011-b4cb-00224802cf58 | m79Pu/mT6SmaOIpTw9Vx0vRHjQUKIgzdbNb4UQgTDTqkPWMyO5i+mCQd2I3SFK7yxspNWY/8a6SJ7+9SMWXrkA== | 2025-10-06 15:27 | 1439 | Implement OpenTelemetry based monitoring for the LIMS environment | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Chris Culberson | NA | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
5eac53f8-9889-f011-b4cb-00224802cf58 | z2Pmgc31P51Oa+uwfSEp1Nm7u+le7mJUANo0ZMe+viu0nQPX0Gizy+X5W5LOjlXwvEuZ8pL+uv62SAWY+G7lFg== | 2026-02-26 19:09 | 1444 | Pilot Azure Data Analysis and ML/AI tools | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Chris Culberson | NA | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
e2f3a2cc-f98f-ef11-ac21-002248080eef | FisBu8YCRbO/buMa4qL2FkyTB7rSlOV0h9AfyDAf/kMqKOObLN6qrfJkFyblxfB0O+R1aATQijAevy1+zFAcHA== | 2025-04-22 10:38 | 1341 | Add more plants to Prometheus APM | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Jeff Brantley | North America;EMEAI | 2024-10-21 16:00 | 2024-10-21 16:00 | 2024-10-21 22:14 |  | 0 | 0 | 0
96efbaa2-5d09-4f62-936d-468477372629 | G1yg8kuEnV8CdOn6lcSXiZVgYxig0yL+uEyoKKybS5QKhD+2wqwD2L3013YfiGbmzFmdLmh2bFWsBs+MrRm7Qw== | 2026-02-26 19:10 | 1508 | Lab instrument PC migration from hybrid deployment to Entra ID | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Chris Culberson | All CAPV, GCO, and Epoxy manufacturing locations | 2025-10-07 14:00 |  | 2025-10-07 23:03 |  | 0 | 0 | 0
ee5ca6c4-0067-4ee8-8e45-57e8a4082af0 | v3jzKKhV709hfH6ycch+ub20owQDIRFhpTOHBoK+g/NuERNZr2nJ1+7UlpKTfuMoppFew6Sp/y5XsBZ7EFfDKg== | 2025-10-13 15:44 | 1509 | SmartPlant migration on ProLytX cloud | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Chris Culberson | US | 2025-10-07 14:00 |  | 2025-10-07 23:07 |  | 0 | 0 | 0
edd941ed-9889-f011-b4cc-6045bd060015 | aw1uMYe/jwSQOJye4blfjs4LB+CVKZk07H3wGtBkjubFn3xI/Yy0QzFjvLM5o9VCKzR4OYKZd/Pq3PJnlVBUUQ== | 2026-02-26 19:10 | 1423 | Level 3 to/from Level 2 communication - CyberSecurity | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Chris Culberson | Global | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
a3592d54-118e-4e0b-8f9f-b10a71682b82 | 29u+s3S9G8NPmCmGsDxBmbXooXb0VjfGsrwczi+FgZj6ADq3HXYWyyHfAS+pJYhYSk9homncXp1J66RjmV2wiQ== | 2026-02-26 19:10 | 1507 | IMDB Feature Enhancements and integration with Olin Applications | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Chris Culberson | Global | 2025-10-07 14:00 |  | 2025-10-07 22:59 |  | 0 | 0 | 0
55f85501-9989-f011-b4cb-000d3a356313 | 4NqMl4sWqusFMqIO0WS0bsBdp5HHBNnIV6zgYUyBzqXwhN8Goeng+LbaQTExG/JGshYsIhuXcwzmAbY8cW1ZYw== | 2025-10-06 15:26 | 1460 | ePAS Safe Work Permit Implementation | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake |  | # ITSBO PPM360 PWAService | Felim Larkin | Chris Culberson | US | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
c9a66504-9989-f011-b4cb-00224802cf58 | fPeM5eZW2xRYMKRmLLuiFWSJewP+OErkop1IxRATaUm7QwlceK8wlL5HpIYQHt2VATKRxc3NzY5TAIB18v7NwQ== | 2025-10-06 15:27 | 1469 | NWA Quality Analyst upgrade or Focus EMI implementation | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake |  | # ITSBO PPM360 PWAService | Heath Corbett | Timothy Baker | TBD | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
44e9620a-9989-f011-b4cb-00224802cf58 | dLEGGiVe1lCnqtikL36tz7qI3mNy+Xw01wcpYardBtrMMpZY3dU4BQ41ILnFG9VvZFOirt4Xs6js+z1DeZVr+g== | 2025-10-06 15:27 | 1476 | LIMS Implementation at Freeport Cl5 | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake |  | # ITSBO PPM360 PWAService | Heath Corbett | Timothy Baker | Freeport | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
c18eb801-9989-f011-b4cc-6045bd060015 | AaJy/jjRpLyOzaFGbCnXQq04BPLh0+C+vQ3PbXETwcaq1b4hGNxHPlI3zpyObXh5WGUEToSBUWM2TVhsH+dqog== | 2025-10-13 14:12 | 1467 | Sphera Essential Upgrade/Replacement | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake |  | # ITSBO PPM360 PWAService | Felim Larkin | Tracy Woodall | US | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
84d0bc07-9989-f011-b4cc-6045bd060015 | AGwV+AKB7xHybG6K/OYOpWm9ZAXzLrjRKqdjZmu9lR4dAvXW37tMNY7+ZjJyrDADcEtOgPXNUjPbQ4/a/xnGUQ== | 2025-10-06 15:28 | 1478 | Laboratory gas chromatography (GC) ML-based data analysis implementation | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Intake |  | # ITSBO PPM360 PWAService | Heath Corbett | Timothy Baker | TBD | 2025-09-04 16:00 |  | 2025-09-04 14:11 |  | 0 | 0 | 0
bdc23cd0-f98f-ef11-ac21-000d3a3161c7 | p8/QxAcMqKkQQ59JdefZR5zL0OWZ/ZDuUn/7gzurHkfBPYPPmr0WW8tuI+7MScgOYmJfalPmdAsKKySumRvndw== | 2026-03-02 21:13 | 1360 | Lab PC OS & HDW upgrade | Olin 2026 | Active | (1) On Track | (1) On Track | (2) At Risk | (1) On Track | (1) On Track | M&E | I.CLA.000027 | Execution | No | Brian Courtney | Heath Corbett | Chris Culberson | Global | 2025-04-01 | 2026-06-30 17:00 | 2024-10-21 22:14 |  | 0 | 0 | 1
60a2eb61-82a4-f011-bbd2-000d3a36e98c | PM3AyS8J1Smkq4KWggG7SP1v45MmPqKE4mrI7HYHlZth4zNMZmIexLLJ817hgtJX79gV72kmKlPJonsWQZB8Ew== | 2026-03-18 14:10 | 1511 | Control Room KPI Dashboards | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Execution | No | Brian Courtney | Nena Fremin | Michael Laflin | Global manufacturing | 2025-11-06 06:00 | 2025-11-06 06:00 | 2025-10-08 20:07 | 0 | 0 | 0 | 0
f6f3a2cc-f98f-ef11-ac21-002248080eef | coYbBabm3ZL9Ox/a0PfOGJ/AbTngvHF4XDW/dslxJbcxg9d3plWFTxbu9Eh4U0BomYBIfc7ZghnFQvYxe9fdRQ== | 2026-03-02 21:36 | 1342 | Splunk Upgrade | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track |  | M&E |  | Execution | No | Brian Courtney | Heath Corbett | Chris Culberson | Global | 2025-12-01 06:00 | 2026-04-30 09:00 | 2024-10-21 22:14 |  | 0 | 0 | 0
06ff1d64-f331-ee11-bdf3-002248081003 | eh91WAYeg5uaP/GZs8HmM4qniAwHPMxSxXeTEhb7u3T5SDsnREniSrkC3i12qIKsG5x8oG6WYNRzc1zHLn2aOw== | 2026-03-02 21:06 | 1231 | OpenLab EZChrom to OpenLab CDS Migration | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E | I.CLA.000024 | Execution | No | Brian Courtney | Heath Corbett | Timothy Baker | FREE, STAD, ANGL, BECA, PLAQ | 2024-01-01 06:00 | 2026-04-30 17:00 | 2023-08-03 11:47 | 0.03 | 0 | 0 | 4
c8429f66-9e31-4864-9052-01519978b074 | IUNal8e8vUg3iXRIqUcZ8fvTtT16oCjU/EC0pkK8H+4U7u/4TJo+L75eAXHyQ/2s5tcGNugw78d61s7dxn5sPw== | 2026-03-20 15:07 | 1169 | 2025 LIMS Dashboard Deployments (phase 2) | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Execution | No | Brian Courtney | Heath Corbett | Chris Culberson | Freeport, Plaq, Stad, Rhein, Balt, Pist, Zhang, Guaruja, Roberta, Bec, Gumi | 2023-01-02 06:00 | 2026-12-31 09:00 | 2023-03-14 22:05 | 0.99 | 0 | 0 | 3
4c142029-b4c7-4455-af48-13d580d4fde6 | EvygBuTCObhy1U18heBPTXGUSrFz3Q5WEK1RIOx4Q+d+dECjIAgeYcphRGgxlaTJEVqQNI2ymoWGBK8P1zpduw== | 2026-03-10 14:27 | 1396 | R2 Electrolyzer Optimization | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Execution | No | Brian Courtney | Christopher Rudy | Steven Tanner | Freeport Plants | 2025-08-04 | 2026-03-31 09:00 | 2025-06-20 16:32 |  | 0 | 0 | 0
cea93ce2-5e7a-ee11-8179-6045bd03b718 | P7snW37WlNLFSOwpeZqp8/+ZdvZHX+axEgwieg8eMQlQMeeyaEal8NHRGTFgDc9Va23WkBGNpviL0rBEj9o+PQ== | 2026-03-02 16:15 | 1241 | Convert OSI PI to IP21 | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E | X.CLA.000026 | Execution | No | Brian Courtney | Elliot Ibarra | Chris Culberson | Heritage Olin (AUG,BECA,CHAS,HEND,MCIN,NIAG,SGAB) | 2024-01-01 06:00 | 2026-06-01 17:00 | 2023-11-03 15:38 | 0.07 | 0 | 0 | 0
604dee79-1b03-470e-8233-bb0d41c9b3e1 | hEbm0uFmwlsZpAhsRBlDdxDJo64p96ToeBFDL8P9V1Au0On/Vh49jPEAbY5z45xUCHPg4ByNfHGVUbunw/tWzA== | 2026-03-02 21:28 | 1163 | Pipe Specification (phase 2) | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E |  | Execution | No | Brian Courtney | Chris Fox | Chris Culberson | Global Chemicals | 2023-01-02 06:00 | 2026-12-31 17:00 | 2023-03-09 19:58 | 0.19 | 0 | 0 | 0
70de6ca8-5a8c-4926-bd67-d68367965172 | m7l/neMZ6/jsAP1lKITXcPdf6G3Ybq4dE/sJ5kBFFqGk39G71Ji2INLoctJevplKD/pOyBHvQiMogY9mzk4M7g== | 2026-03-10 14:27 | 1392 | Global Prometheus APM Rollout | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | M&E | X.CLA.000042 | Execution | No | Brian Courtney | Christopher Rudy | James Barrington | Chemical Plants Globally | 2025-05-15 09:00 | 2026-07-31 17:00 | 2025-05-15 16:23 |  | 0 | 0 | 0
8dc23cd0-f98f-ef11-ac21-000d3a3161c7 | Rdk4CyXdji/ZkJ5/YrMcJcd6Lvt+nbVjlrqewBgV+CbecTxtMSVSuZT6DA21eZTYKzHaBMDI190hY+oxZX7ehw== | 2025-10-13 15:46 | 1357 | Radford AA IT RFP | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Lisa Humphreys | Dennis Bailey | North America | 2024-10-21 16:00 |  | 2024-10-21 22:14 |  | 0 | 0 | 0
8a0b423d-fcbf-f011-bbd3-00224802cf58 | +WIzJynmQKT1onCki8KWS4LBFHgZ12mVvkRKVvYeIiVoC980FyLQj7TpglsjMBuM3UfbLjbw4Ds9RNlhId7mrw== | 2026-03-30 17:59 | 1515 | Winchester Transportation Management | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Intake Gate 2 | No | Raghu Garine | Raghu Garine | # Bailey, Dennis WINCH | EALT, OXFD, WF | 2025-11-12 17:00 | 2025-11-12 17:00 | 2025-11-12 19:18 | 0 | 0 | 0 | 0
5b8a86f1-34d1-f011-bbd3-00224802cf58 | NTSY/pI2zBfZ48kBFNaQ+6Vy/rijlJRkapRhYTgDUkY5iMjfza3GmN34qdniiW45TC7oy2wN4k65MCbBEFZk0Q== | 2025-12-15 13:50 | 1517 | GuiXT Ugrade to LiquidUI | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Intake Gate 2 | No | Brandon Kamp | Brandon Kamp | # Bailey, Dennis WINCH | EALT, OXFD | 2025-12-04 17:00 | 2025-12-04 17:00 | 2025-12-04 17:16 | 0 | 0 | 0 | 0
3d399bd2-f98f-ef11-ac21-002248080eef | +20/t51ftMpMpX1jL1V90XLd+HE+rXJwRJKOqBayB9or77C6TUTHDZaY6+qRm2B4uiRq2shmYZ2EJIkVdfNAJQ== | 2025-03-03 16:49 | 1361 | SAC Upgrade | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Steve Holt | Dennis Bailey | North America;EALT, OXFD, E-TECH, Clayton | 2024-10-21 16:00 | 2024-10-21 16:00 | 2024-10-21 22:14 |  | 0 | 0 | 0
59399bd2-f98f-ef11-ac21-002248080eef | iEY+sKVI9wDA03mSxeQyBV/hznX973BZ42nZ9HKoOnPUIXvRMXWvAMQAT5N6FP2C+k3x94EmkUINh4SE1n7nVg== | 2024-10-21 22:18 | 1364 | Hyland Replacement - Costpoint AP Processing | Olin 2025 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Lisa Humphreys | Dennis Bailey | North America | 2024-10-21 16:00 |  | 2024-10-21 22:14 |  | 0 | 0 | 0
50811944-5a0a-42d7-a1d1-8dbbc6098ae1 | +9aFQAsRKfZTFSMQi2wqt1t+EyJeXsY1eWtjoesHEbr+zVQTPVwLHlIf//YW4T/0NOTCJEB/GifRtpymlmBmvw== | 2025-11-04 15:21 | 1510 | Project Valiant Radford | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Lisa Humphreys | # Bailey, Dennis WINCH | Winchester | 2025-10-07 14:00 | 2025-10-07 14:00 | 2025-10-07 23:11 |  | 0 | 0 | 0
c1c26f4e-4cbe-f011-bbd2-000d3a5bdd18 | G7WA4tawCJKtOvfdLJv930i6Hnpbq2WnFDvYgow+e229FWs1E1QBWODQ4zMPEux5uHoGpju3u7sziXsGNWf5oQ== | 2026-03-30 19:41 | 1513 | Sterling EDI to SAP Integration Suite | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Execution | Yes | Michelle Kissell | Brandon Kamp | # Bailey, Dennis WINCH | All Winchester and White Flyer Sites; LCAAP | 2025-12-09 06:00 | 2026-11-26 09:00 | 2025-11-10 15:46 | 0.17 | 0 | 0 | 0
a828b209-2063-f011-bec2-00224802cf58 | 7FwgRq18D2/9pHuCVmMQMCGGfOd9sYf/JTCRqKHM07KuUIPNspKXmkWQKzx0yfOWHw44EeyaPe817w/LpQOTAQ== | 2025-12-19 15:59 | 1404 | WIN AUS - Pronto Cloud | Olin 2026 | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Execution | No | Darlene Schumer | Brandon Kamp | Dennis Bailey | Australia | 2025-08-14 | 2025-09-30 17:00 | 2025-07-17 15:10 | 0 | 0 | 0 | 0
195e2524-ace1-4f1f-8619-1749a2a84554 | 1IIWw6Rk4P3R1QYTobYm3y1SDnS2miXuECOORX3afvKS8kibIZ+gLdhDUqz22RirwbO6A+pK5BWAoOAvo61l5w== | 2026-02-13 19:14 | 1534 | TEST Project |  | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Execution |  | Darlene Schumer | Darlene Schumer | Darlene Schumer | All | 2026-02-06 15:00 | 2026-02-06 15:00 | 2026-02-06 19:54 |  | 0 | 0 | 0
b9ff1feb-0025-4088-b98d-23cf493bad18 | UnTrC5bS9a1lfJhXU/wXXP8ISYWiJXwaHVfktjskDpEnAh3tIjwzeOWV7Ehq6YfaxZE17uNN83Qa6NzIqiRPBA== | 2025-10-21 19:01 | 1486 | (Hold LCAP) CMMC 2.4: Commercial Cloud Application Inventory | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Execution |  | Darlene Schumer | Dennis Bailey | David Kellar | Winchester locations | 2025-09-08 09:00 | 2025-12-31 09:00 | 2025-09-08 20:11 |  | 0 | 0 | 0
19fb538f-3713-45ae-8581-3a16fec79fda | q309g4PJJQUmljXrFI2q0FtCGmcTqwUzi4Q/GbTi10648dvHrbnaaleEBNoDbQnEkO7qdc6ZW0uZWDY6dECJjQ== | 2026-03-30 18:25 | 1488 | CMMC 4.2: Rewrite/Upgrade Applications on Unsupported Operating Systems | CMMC Remediation Portfolio | Active | (2) At Risk | (1) On Track | (2) At Risk | (2) At Risk | (1) On Track | Winchester |  | Execution | Yes | Seth Aldrich | Dennis Bailey | David Kellar | Winchester locations | 2025-10-01 | 2026-07-16 17:00 | 2025-09-09 18:59 | 0.75 | 0 | 1 | 1
4ccc1402-4e79-466a-b697-bc48faa58483 | AmoOlBURRSEoVR+F22tr4hBmPr8AnQ77UK46z37nw4fYlx8uv1iaQeKqKvldqa7tXNZev0xj8T0dfwE1MmIBIQ== | 2026-03-30 19:31 | 1484 | CMMC 2.1: Infinity QS System & Shared PCs | CMMC Remediation Portfolio | Active | (1) On Track | (1) On Track | (1) On Track | (1) On Track | (1) On Track | Winchester |  | Execution | Yes | Michelle Kissell | Dennis Bailey | David Kellar | Winchester locations | 2025-09-22 | 2026-11-18 17:00 | 2025-09-08 19:55 | 0.38 | 0 | 0 | 0
36f074b1-0076-4b1d-bf22-cc9450c005f5 | 5vNXQQhF4fPTC34MvbWK7Wy8Je1MDKmEfOHnsgIejMjDKMlwSBOcR3wHbzHMdJZASAoqHhZTF54KVs/T69D+dw== | 2026-03-30 18:34 | 1485 | CMMC 2.3: Unmanaged Local Applications | CMMC Remediation Portfolio | Active | (3) Off Track | (1) On Track | (3) Off Track | (1) On Track | (1) On Track | Winchester |  | Execution | Yes | Michelle Kissell | Dennis Bailey | David Kellar | Winchester locations | 2025-08-01 | 2026-01-02 17:00 | 2025-09-08 20:04 | 0.72 | 1 | 0 | 0 | 55000 | 55000

## hiddenSheet (hidden)
msdyn_project:sbWrAuJK8+K2b8wGjlFD6BOLeFUeCvZaC3YxAigYHzs8GBkYysk3vr/trWdvuXlTOg3hrgRHqmL6gNOsNo0hQA==:msdyn_projectid=%28Do%20Not%20Modify%29%20Project&checksumLogicalName=%28Do%20Not%20Modify%29%20Row%20Checksum&modifiedon=%28Do%20Not%20Modify%29%20Modified%20On&m360_projectid=Project%20ID&msdyn_subject=Name&m360_portfolio=Portfolio&statecode=Project%20Status&m360_overallhealth=Overall%20Health&m360_budgethealth=Budget%20Health&m360_schedulehealth=Schedule%20Health&m360_resourceshealth=Resources%20Health&m360_scopehealth=Scope%20Health&m360_itdepartment=IT%20Department&m360_cpmsprojectnumber=CPMS%20Project%20Number&m360_currentstagename=Current%20Stage%20Name&m360_itpmrequested=IT%20PM%20Requested&ownerid=Project%20Manager&m360_requestor=Requestor&m360_businesssponsorchampion=Business%20Sponsor%20%2f%20Champion&m360_locationsimpacted=Locations%20Impacted&msdyn_scheduledstart=Start%20Date&msdyn_finish=Finish%20Date&createdon=Created%20On&msdyn_progress=%25%20Complete&proj_activechanges=Active%20Changes&proj_activeissues=Active%20Issues&proj_activerisks=Active%20Risks&m360_actualcapex=Actual%20CAPEX&m360_actualcapex_base=Actual%20CAPEX%20%28Base%29&m360_actualopex=Actual%20OPEX&m360_actualopex_base=Actual%20OPEX%20%28Base%29
Active | Inactive
(1) On Track | (2) At Risk | (3) Off Track
(1) On Track | (2) At Risk | (3) Off Track
(1) On Track | (2) At Risk | (3) Off Track
(1) On Track | (2) At Risk | (3) Off Track
(1) On Track | (2) At Risk | (3) Off Track
Ent Solutions | GIS | HR | I&O | ITSBO | M&E | Winchester
Yes | No