## All Projects 2
(Do Not Modify) Project | (Do Not Modify) Row Checksum | (Do Not Modify) Modified On | Project ID | Name | Portfolio | Project Status | Overall Health | Budget Health | Schedule Health | Resources Health | Scope Health | IT Department | CPMS Project Number | Current Stage Name | IT PM Requested | Project Manager | Requestor | Business Sponsor / Champion | Locations Impacted | Created On | % Complete | Active Changes | Active Issues | Active Risks | Actual CAPEX | Actual CAPEX (Base) | Actual OPEX | Actual OPEX (Base) | Project Type | Planned Initiative Start Date | Start Date | Planned Initiative End Date | Finish Date | Planned Project End Date | Planned Project Start Date | ARB Status | EA Solution | Work Council Status | Work Council Outcome | AI CoE Status | Intake Notes | Intake Score | GTG Plan
93227cf1-fad9-f011-8544-000d3a356313 | cIo9/CnuoLb/Iorz2UeplOQZWwHKwsk5lpxrz/cwdix/l7/HRwJe3hrB55ezLj0ZCK4ONXH34YcBW3O558ZOGQ== | 2026-02-26 19:13 | 1527 | Nakisa replacement | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Jeanie Thompson | Global | 2025-12-15 21:14 | 0 | 0 | 0 | 0 |  |  |  |  | Discovery | 2026-01-15 | 2025-12-15 17:00 | 2026-03-31 | 2025-12-15 17:00 | [8 empty] | 1.96
1ff85501-9989-f011-b4cb-000d3a356313 | 1fJywtupDx5mE9sGjR8V/lVkmj4EYbBnxiUPLcCZIXFaKhQZyNz69qoScy3xNA+LB1PS5q67UGrBAnhU6Ypnig== | 2025-10-30 14:02 | 1454 | Rio 2026 | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Ent Solutions |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Kathy Seifarth | Kathy Seifarth | Brazil | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2026-01-01 | 2026-01-01 06:00 | 2026-12-31 | [9 empty] | 123
e953ffe5-9889-f011-b4cb-00224802cf58 | DvROgSrIGfHNyBSbmNHIxOf0T/AidDQnXVpYefMWSOTSpI3LDOpl2rOlfP1H2SdFk6ee9ccYwmSrLqegalqIjw== | 2026-02-26 19:08 | 1414 | Implement EAM Extension for Plant Maintenance Objects (FLOC, Equipment, MBOM) | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Ent Solutions |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Allyson Taylor | Kathy Seifarth | All Chemicals manufacturing/maintenance locations | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2025-01-01 | 2025-09-04 16:00 | 2026-01-01 | [9 empty] | 123
aaa018f2-9889-f011-b4cb-00224802cf58 | 3EJDXx8IktVQFMQX7EeDusMZGwC514xLwkZuNmciPeC2t1yxAMs44/YBuol+wEKOrPNhd2t4UYExKXh3Arqyyw== | 2026-05-11 18:09 | 1429 | Migration to SAP Business Data Cloud (BDC) | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Ent Solutions |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Kathy Seifarth | Kathy Seifarth | Global | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2025-04-01 | 2025-09-04 16:00 | 2026-01-01 | 2025-09-04 16:00 | [8 empty] | 123
823c8230-2601-f111-8406-00224805f204 | zR0Rw4nvurN2femawrKuuNwP9mQ6zD5sy6cTfuYlySZoBsmUjdtULTxUf4UrTDYk0HkzMp+XYcoImm/qK5vTQw== | 2026-03-10 14:24 | 1532 | Bourque Logistics | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Kathy Seifarth | Global | 2026-02-03 17:32 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-03-04 | 2026-02-03 17:00 | 2026-12-31 | 2026-02-03 17:00 | [8 empty] | 2.95
c9a3ac40-01da-f011-8544-6045bd060015 | +/PH0GAk/QG9bzRxxcX44JBwyT01pLPI6vIxzm2z5mweF/wncJHbv3oP63krZSAL6SdMlkYT0K3EzaAbtLxxZA== | 2025-12-15 22:02 | 1528 | AES32 Time Management Module | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Matthew Stewart | Freeport, Plaq | 2025-12-15 21:59 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-01-13 | 2025-12-15 17:00 | 2026-09-01 | 2025-12-15 17:00 | [8 empty] | 3.45
03a36646-f6d9-f011-8544-6045bd0857df | SCNTxHdfjre4aVKgyzBuSeS0xilzbCa4b5htgm5ZotLxA/fHxCaVP5XBZKM2DHKaiKZGmNI9R+AIy1wW9S83Rw== | 2026-02-26 19:10 | 1526 | Project SOPrano | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Alex Weir | Global | 2025-12-15 20:40 | 0 | 0 | 0 | 0 |  |  |  |  | Discovery | 2026-01-13 | 2025-12-15 17:00 | 2026-03-31 | 2025-12-15 17:00 | [8 empty] | 2.21
31b40e0c-2601-f111-8406-7ced8d3be8bf | gUG48pcInYIjO+PRuJCfW4j5pAq03YQ+NB2LhvlQYx27FYKUwTiVKTmGWXgnoniYjnSjsI0XDt9CBGQacgHizA== | 2026-02-25 18:09 | 1531 | GTS Upgrade | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Ent Solutions |  | Intake Gate 2 | No | Kathy Seifarth | Kathy Seifarth | Kathy Seifarth | Global | 2026-02-03 17:31 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-03-04 | 2026-02-03 17:00 | 2026-12-31 | 2026-02-03 17:00 | [8 empty] | 3.1
35c65d1d-f6d9-f011-8544-00224802cf58 | VCRmRJtDIfJ0uRIQxxhvRnrVc6LYikBb+tAGuFdtN2r8+HlikQjK+KDmfkHU9+oeQfKIpCTcccz5Centx1c9IQ== | 2026-06-01 21:14 | 1525 | SAP Document Compliance_Germany and Italy | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Ent Solutions |  | Execution | No | Seth Aldrich | Kathy Seifarth | Rosanne Richter | Germany and Italy | 2025-12-15 20:39 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-05-01 | 2025-12-15 17:00 | 2026-09-01 | 2025-12-15 17:00 |  |  | ARB Required | Simple Solution | Work Council Required | Work Council paper work is in work. May only be notification not full work council approval. | AI CoE Not Required | Discuss Interfaces with SAP Doc Compliance prior to Go Live. | 3.11
4e995dfb-9889-f011-b4cb-000d3a356313 | B11Ah5C8Ur+hWEi81qaDPohMtnjTxgOlro31zAo0vVgGm4wK/I+4x8VdGwzRQOd5pISiB3eR+pyUkZI+V72KXA== | 2026-04-28 23:47 | 1450 | OT Cyber Security Awareness Content | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | IT Steer Co Approval | No | Md Uddin | Nathan Faith | Dennis Allen | All | 2025-09-04 14:11 |  | 0 | 0 | 0 | [6 empty] | 2026-05-01 05:00 |  | 2027-11-25 09:00 |  |  |  | N/A | Work Council Not Required |  | AI CoE Not Required | 4/2: - This is only for awareness purposes and not changing any rules/requirements/policies for workers. - Need to understand quiz vs testing in regards to Germany Work Council - Will include both Chemicals and Winchester - | 123
5c4c3dca-f98f-ef11-ac21-000d3a3161c7 | QiEUO9WHUabPMAxie2UF/o5SAtO9UpxVCi4OykXACh7gvOFD9OrQIvkbovGkH0AWldiEZT5TCz82U8dHc6J1ew== | 2026-03-31 17:56 | 1334 | Network Access Control (NAC) ClearPass | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Margaret Broder | Dennis Allen | Global | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-01-01 | 2024-10-21 16:00 | 2025-01-01 | 2024-10-21 16:00 | [8 empty] | 123
40995dfb-9889-f011-b4cb-000d3a356313 | LOcvw82erGr1T+j+XawPXrIGcTH+sjQ0bnFC2t4hI4oifE6KRyokiCJA8vCQGmN113uypbQKlcKXTRtn4EXHQg== | 2026-02-26 19:14 | 1448 | Netskope - China POP | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Steven Beasley | Dennis Allen | China | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2025-01-01 | 2025-09-04 16:00 | 2025-04-01 | [9 empty] | 123
ca0ed10d-9989-f011-b4cb-000d3a356313 | Fr27b0wgdeaf6Owt5dnfmYTs+GpQw5M0riGqZVTgWkxcqLf1nC3umMHlk5vBfqFePEtHIW1Ki22DKKayCko9Fg== | 2025-10-06 15:26 | 1482 | Cyber Security Awareness Training Platform | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nathan Faith | Dennis Allen | ALL | 2025-09-04 14:12 |  | 0 | 0 | 0 | [6 empty] | 2025-09-04 16:00 | [10 empty] | 123
6e163ecd-f98f-ef11-ac21-000d3a3ae441 | qB6N9IWi4QlvLEdZmV86IqC41kK/CLOOh595GG8apNCPiTO6T6Xg7IuBmlmHx2zCwKKDEbuz6FqGkoLIMB68kA== | 2024-10-22 02:27 | 1340 | Application Development Discovery - Secure Development | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Margaret Broder | Dennis Allen | Global | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-01-01 | 2024-10-21 16:00 | 2025-01-01 | [9 empty] | 123
bc639595-0e87-ef11-ac21-002248080eef | yDZYe7ugdNeJP303x/MgCf1qsvOjEtm/gc3YusXh28JiZB4JHpaHxIrz2Fb9ecMlVLizrlIF5DEnqbDYG7272Q== | 2025-10-13 16:28 | 1330 | CyberSixGill - Dark Web Monitoring | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS | x.cla.000029 | Intake Gate 2 | No | Steven Beasley | Steven Beasley | Dennis Allen | No direct impact to users, will provide server for Senior and Exec Management | 2024-10-10 13:50 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2024-11-08 | 2024-10-10 16:00 | 2025-01-31 | 2024-10-10 16:00 | [8 empty] | 2.2
fcd8f600-d25e-f111-a826-6045bd050c4d | CqO3DqKbfc1VY60GH7LJdorPGnaPB1Q/Qqpcs/s82FjTEZvELT4AmFk4BCj7MC7sf7LcG3ZI+mdujuDjdbR8GQ== | 2026-06-03 22:30 | 1547 | Dragos POC | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Intake Gate 2 | No | Rishi Master | Rishi Master | Dennis Allen | Plaquemine HotRack | 2026-06-02 22:26 | 0 | 0 | 0 | 0 |  |  |  |  | Discovery | 2026-07-01 | 2026-06-02 16:00 | 2026-08-31 | 2026-06-02 16:00 | [8 empty] | 3.6
0bf3a5bb-ebf0-40c0-9261-d89f4cb5acaf | 1q+tjPcftNXRsX4S2sw2qC1Mfk2pEFQ4riWuzIYoT2yAvp+VDOxgZvgKNTcZAKuTJbcFBUTkWbLUgELgWvP4LQ== | 2026-02-26 19:09 | 1495 | CUI Boundary Diagrams LCAP (HOLD) | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Dennis Allen | David Kellar | Winchester locations | 2025-09-10 17:43 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-06-01 | 2026-06-01 | 2026-12-31 | 2026-12-31 09:00
c0359777-f40b-474b-b12a-f2ea54e0ac3e | psJCBXLyNTBlxNXd4/WGBK1s6qcyOsqiuTipFXTPeooLXyOf2bW+DBGkYhvn089fwhNxfSWnJF9wDIVX+Zp/TA== | 2025-12-05 19:42 | 1496 | (HOLD) CMMC 2.5: Security Protection Assets (SPAs) | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Intake Gate 2 |  | Darlene Schumer | Dennis Allen | David Kellar | Winchester locations | 2025-09-10 18:22 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-10-06 | 2025-10-06 | 2026-03-31 | 2026-03-31 09:00
2a995dfb-9889-f011-b4cb-000d3a356313 | Q5sIoQ8fPa8e9ACNY3Lj8L0KXWBAx+/7eosnFthx7gaDenrIDXIjcMJQZ6pKKwQC1pmYgYd1fJAuFZFZzGtXuA== | 2026-05-26 16:18 | 1447 | NIS2 Compliance Assessment and Readiness | Olin 2026 | Active | 🟡 At Risk | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟡 At Risk | GIS | X.CLA.000049 | Execution | Yes | Bob Cassout | Nathan Faith | Dennis Allen | Chemical HQ, Germany, Italy | 2025-09-04 14:11 | 0.73 | 0 | 1 | 0 |  |  | 64221 | 64221 | Implementation | 2025-12-01 | 2025-12-01 06:00 | 2026-06-30 | 2026-06-30 09:00 | [8 empty] | 123 | Review Gap Report for the German sites with the team and draft plan of action
2ef85501-9989-f011-b4cb-000d3a356313 | tm4eWV0daNaZ9wCRGRSxk0F6xifcQ72cXbjX6Yb/MXOUaACEIEb0CDNmtEVvRMZP0UpA1aHbblOu9sJjTBWWKw== | 2026-06-03 19:00 | 1455 | Onapsis Defend Implementation | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS | N/A | Execution | Yes | Bob Cassout | Nathan Faith | Dennis Allen | Winchester and Chemicals | 2025-09-04 14:11 | 0.04 | 0 | 0 | 0 |  |  | 1332 | 1332 | Implementation | 2026-01-01 | 2026-01-01 06:00 | 2026-07-03 | 2026-07-21 17:00 | [8 empty] | 123
a64610f2-d5a2-f011-bbd2-000d3a59edd5 | 8xMOWNXHphvQCoqGxbebyyEfRAICgPWpaj9BXQb8B77z8By88GPL5pNEUzNg4/uKUEZHYDfKWi0MSdUNQKt6hw== | 2026-05-21 12:54 | 1503 | SentinelOne Cloud Security POC | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Execution | No | Bob Cassout | Steven Beasley | Dennis Allen | Global (Not Germany for now) | 2025-10-06 17:01 | 0 | 0 | 0 | 0 |  |  |  |  | Discovery | 2025-11-04 | 2025-11-04 06:00 | 2025-11-28 | 2025-11-04 06:00 | [8 empty] | 3.65
a6857c61-30b5-ee11-a569-6045bd03b718 | CAfIC6sBmAppKuX9IfgUWPrm8DpjQtnZQCp2Q2Vywdb+0xGyONY6l20hZO6w/CGoBH6xa4JV3JQLJLMEhggidg== | 2026-05-26 15:16 | 1248 | Armis OT Collector Deployment | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS | TBD | Execution | No | Bob Cassout | Michael Ehlers | Dennis Allen | Plant locations | 2024-01-17 12:03 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2024-04-29 | 2025-01-06 09:00 | 2024-12-27 | 2026-12-03 17:00 | [8 empty] | 2.85
8e2db857-19a5-f011-bbd3-6045bd060015 | WEcFm+EYGQqHq+55Fzy58wjviTdyB1HSd4znMyfDV5JIOpdQYHvWsQR35ZdTfm07B0cTAbGB7kbics/5vRGK8A== | 2026-05-27 13:02 | 1512 | KnowBe4 | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Execution | No | Bob Cassout | Jason Vogel | Dennis Allen | All | 2025-10-09 14:08 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-01-03 | 2025-12-01 06:00 | 2026-03-31 | 2026-03-31 09:00 | [8 empty] | 2.1
a58666e8-26d1-f011-bbd3-6045bd060015 | 29br3uv9nIv+VVa3LHPlcswK7kHD84bcuV3LhW+okRpqT3TQkgj7mtfHxwfvJf/R1gyhUiPx3E0evFfjP+UmzQ== | 2026-05-26 23:06 | 1516 | Archer NIS2 Tracking Implementation | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Execution | No | Bob Cassout | Adam Barletter | Dennis Allen | Chemicals | 2025-12-04 15:36 | 0.51 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-02-02 | 2025-12-04 17:00 | 2026-05-29 | 2026-05-28 09:00 | [8 empty] | 2.7
48a68166-317a-4f1e-8ca5-72f5070efb98 | eHlOkW35ceCRB2h5GCEoZk0CE4oWwXHQCdjTe3Vgfktq+DGfEgmRE8TL0TC6GsKO6oBqfBDV+ohFzfZ8VmL/Cg== | 2026-05-26 15:22 | 1504 | OT Remote Access Solution | Olin 2026 | Active | 🔴 Off Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🔴 Off Track | GIS | X.CLA.000048 | Execution | Yes | Bob Cassout | Steven Beasley | Dennis Allen | US | 2025-10-07 18:45 | 0.72 | 0 | 0 | 0 |  |  | 1333 | 1333 | Implementation | 2025-11-03 | 2025-11-03 | 2026-08-31 | 2026-06-12 17:00 | [9 empty] | The on-prem vs cloud stuff issues appear to have been resolved, but each site is showing that we need to be agile because each OEM (ABB, Siemens, Emerson) have shown to be a challenge. Once the OEM challenges are addressed the project can turn green.
1fc5e67c-51fc-4ed3-a7d0-7466c6bc1b42 | 6Az1SeU/CIWLLcy/4Q3D6FuS/3O0xesA5QVDvuyzw1VSLdiCELENG0mlrAlARkw7TrUPbJCy4lD8B54GQ0N2kA== | 2025-11-05 23:32 | 1120 | CMMC 7.1: EALT Purdue Model Implementation | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS |  | Execution | No | Bob Cassout | Steven Beasley | Rory Lynch | East Alton | 2023-02-03 21:19 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2024-06-03 | 2024-06-03 05:00 | 2025-12-26 | 2025-12-19 14:00 | [8 empty] | 3.2
19054702-8031-47c8-af22-f3686c8800da | 0tj2COGTTiQoehC7Y8/jsmfoWwiAZvgi+Dn/6onZqNHUDfF/1MqyVFPn06wxqjpUiINcwSSovGyqw9CLv+SiuQ== | 2025-12-01 17:27 | 1265 | CMMC Certification Readiness | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | GIS | 240068 | Execution | No | Darlene Schumer | Margaret Broder | Dennis Allen | Winchester locations | 2024-02-14 21:42 | 0.93 | 0 | 0 | 0 |  |  |  |  | Implementation | 2024-10-30 | 2024-10-07 05:00 | 2025-12-31 | 2026-05-12 17:00 | [8 empty] | 2.85
a4314354-b923-f111-8341-000d3a36aadd | Mmy25WxxeOODnzkh2VT93fnPgJaoS7IxBqt2sgJCz6tlYa8WNW2DvoDOmgq4Ts7l6dspMbQUePALUDQTd6LGHw== | 2026-04-23 14:28 | 1536 | UKG Clock Replacements - Chemical Locations | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | HR |  | Intake Gate 2 | No | Carolyn Henderson | Carolyn Henderson | Carolyn Henderson | Chemical Locations | 2026-03-19 17:31 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-07-01 | 2026-03-19 16:00 | 2027-04-01 | 2026-03-19 16:00 | [8 empty] | 2.7
1c4efc88-2d76-4fb4-8c27-c15417fa4798 | qUI9NkI9BfNED+tg1UvYUi+fUIfpM5vfCsOTZ2B1tXA5gmM/PLl0Nq7K4gV4uZhlzg+AKqbNT6aSAHleMg9W8w== | 2026-04-13 16:41 | 1151 | Becancour Kronos Implementation | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | HR |  | Intake Gate 2 | No | Carolyn Henderson | Jonathan Brewer | Carolyn Henderson | Becancour | 2023-02-15 21:04 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2023-04-01 | 2023-02-15 09:00 | 2023-09-01 | 2023-02-15 09:00 | [8 empty] | 3.75
74a84624-443e-ef11-8409-00224808f30b | N3LbOYL8KVSQK+ArdR1LWPx1MaqFbxm9hoFDh5lp3414V7sQ0r8yYK8mbjg0T/sBkuudB04R58nbh8VQJCuCww== | 2026-06-03 18:40 | 1311 | HCM Replacement | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | HR | I.CLA.000032 | Execution | No | Brian Courtney | Carolyn Henderson | Valerie Peters | Global | 2024-07-09 22:40 | 0.61 | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-01-06 | 2025-01-06 06:00 | 2026-09-30 | 2027-09-30 09:00 | [8 empty] | 3.41
091aabda-bf7f-4452-912a-1413ba519d60 | 2/YgS7WXE3X3fMywP6ymN3X/9S0wisM6xqjvpOwyaqpQ/xdSRZNNIrF9zqnKFEFbUsaWY3KsCO8nD98ETMbCyw== | 2026-04-30 16:37 | 1505 | UKG Dimensions Germany | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | HR | I.STA.000003 | Execution | No | Brian Courtney | Carolyn Henderson | Stephanie Brandenberger | Stade, Rheinmuenster, Baltringen | 2025-10-07 22:28 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-03-01 | 2025-10-07 14:00 | 2026-10-01 | 2026-10-01 17:00 | [7 empty] | 2/2 - Working on Scope with Work Council to determine go forward. (solution cannot delete partial data)
b1580cc6-04d0-4e9a-a171-7e69ba662b14 | WbHVv5rsHi6BTdSr/ghyEcRFCy6eCJFpQotqUEJ2w/K9+L+YednZcKbP0IGm4DNwwGemsfMXgOwZc+FUEcVjUQ== | 2026-06-01 21:17 | 1492 | CMMC 6.1: IAM/IGA Implementation | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | HR |  | Execution | Yes | Seth Aldrich | Jeffrey Miller | David Kellar | Winchester locations | 2025-09-10 17:33 | 0.87 | 0 | 0 | 0 |  |  |  |  | Implementation |  | 2025-09-10 09:00 | 2026-03-31 | 2026-06-30 17:00 | [9 empty] | .
51c23cd0-f98f-ef11-ac21-000d3a3161c7 | AX2/QQynqRRvA6gq7N+wwYF6/boXYZhQ5uxtDvWSQJ5kU83aCwcSGKP3nuiC08SEwwapHa3T9Fg2sklOaG1vkA== | 2026-01-28 20:19 | 1351 | ESX Server Upgrades | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Andy Pilgrim | Mike Somers | North America;EMEAI | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2026-01-01 | 2024-10-21 16:00 | 2026-12-31 | 2024-10-21 16:00 | [8 empty] | 123
3d4fa2f2-c602-f111-8406-002248097567 | 7tQj0qhPnBOy2hK4Er8H0mw70rALG/7OABbDxCXp3ThyjZ5wmGih/YPWjY3tuSeyJWFMPQZwu3xII6JWPjj24Q== | 2026-04-23 14:28 | 1533 | Unified Communications Discovery Project | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O |  | Intake Gate 2 | Yes | Michael Boone | Michael Boone | Mike Somers | East ALT, Clayton , Houston & Oxford | 2026-02-05 19:15 | 0 | 0 | 0 | 0 |  |  |  |  | Discovery | 2026-03-06 | 2026-02-05 17:00 | 2026-06-30 | 2026-02-05 17:00 |  |  | ARB Required | Complex Solution | Work Council Required | Before Deploying in EU would need to review with Owen on shifting from Cisco to MS Azure. | AI CoE Not Required | POC for module of Team Voice. Current state this we are utilizing WebEx. Conducting MS Teams Voice Proof of COncept. will conduct some UAT Testing. Potientially move away from WebEx. Would need to conduct Architectural Design. There are desk phones that would need to remain. Okay for Work Council to move to Steer Co for Discoverr, but before depolying would need to be approved thorugh Work Council. Additional Design Discussions would need to happen as part of the POC. - There may be technical gaps that need to be document and reviewed as part of the POC. - Review existing contract with Cisco on any implications with transitioning to Azure. - Actions: - Review Priorities with Mike Somers for this project compared to CMMC Rememdiation. - Need Financials Documented for POC - | 1.7 | Finalized PSTN connectivity decision (documented) Pilot user list with role rationale Number eligibility matrix (keep / optional / retire) E911 design summary Pilot success criteria & exit checklist Microsoft Teams Voice is Microsoft Teams’ enterprise phone system. It allows users to make and receive traditional phone calls (PSTN calls) directly inside the Microsoft Teams app using a phone number—replacing or supplementing desk phones and legacy PBX systems.
9d5f535e-cd20-454e-904b-51795995c2f5 | rMN7YSmEHS6Y4yaHGKcBE4/3KY6k2x6l3VJxEwRmKaui73ahuKXOLZ2/l6l7tU0zuzWU7t/RAzPY7NSKlF2XSQ== | 2025-10-06 15:28 | 1494 | Separate IT OT network at Lake City | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O |  | Intake Gate 2 | Yes | Mike Somers | Mike Somers | David Kellar |  | 2025-09-10 17:41 |  | 0 | 0 | 0 | [5 empty] | 2026-06-01 | 2026-06-01 | 2026-12-31 | 2026-12-31 09:00
13d005de-f695-4763-96f3-c2f214c6440d | JvqhIofSLlZgIbe5+j6o4YLLKDJ458t3hIwocNh8wAnFZpEQ60VvucrulqZi9UnnU/6+c6c26Hgn/Kw8/gnGkA== | 2026-02-25 18:16 | 1497 | NAC Implementation Strategy LCAAP (HOLD) |  | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Mike Somers | David Kellar | Winchester locations | 2025-09-10 19:13 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-06-01 | 2026-06-01 | 2026-12-31 | 2026-12-31 09:00
24c23cd0-f98f-ef11-ac21-000d3a3161c7 | ABQEnXXAideGVhNyJMeUhvaRNa4jKm5vebvjNdQqf+NQydIz96EGztPCEDehYm9YC3nBZiMQnosEiFYyTisTAw== | 2026-06-01 13:07 | 1345 | Remote Access Solution Replacement | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O |  | Execution | No | Jeff Dahl | Ajay Vedre | Mike Somers | Global | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2025-12-01 | 2025-12-01 06:00 | 2026-12-30 | 2026-12-30 09:00 | [8 empty] | 123
7539fa28-b1a0-4335-9930-07c6e2ebe56e | dXVNA9f5N5OCcQtFG8SPeBLK6876Volpve6m5ZQY/aXyfBFWbxSs8PWPcwJUni0fGWb+KEvhxorzhIVTXRN17Q== | 2026-06-01 13:09 | 1132 | SDWAN deployment | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O | X.CLA.000008 | Execution | Yes | Jeff Dahl | Michael Boone | Mike Somers |  | 2023-02-03 22:23 | 0.55 | 0 | 0 | 0 | 0 | 0 | 68767 | 68767 | Implementation | 2023-01-30 | 2023-02-03 09:00 | 2026-12-18 | 2026-12-18 17:00 | [8 empty] | 3.25
9c6b10c7-a371-421f-a089-0863dd0a2014 | BzraTay1uYwVJFaw7Z271vRmkZ51wzsv8hTZ9GYVydmfXQ2ZmVp1hO6yVQuFU6SgBqhMlPZkZPX/l0Dvq9q1hg== | 2026-05-26 12:48 | 1380 | 2026 Server Room Power supply requirements | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O | X.CLA.000051 | Execution | No | Jeff Dahl | Ajay Vedre | Anthony D'Amato | EALT | 2025-03-21 14:43 | 0.1 | 0 | 0 | 0 |  |  | 206 | 206 | Implementation | 2025-04-01 | 2025-04-01 | 2025-12-31 | 2026-12-17 17:00
3e2e271d-efb3-4013-9f8e-53ae120cde2c | IEWiwmZ0IZjof5jJVXwWqUSgXDc5pEfzuQ1AFYtV/7TPZA9/jZhsRp3nvdfCEmFxsPFR1okDBAdxogljHMifIg== | 2026-06-01 13:06 | 1129 | Network Switch Replacement - Cisco Audit | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O | X.CLA.000027 | Execution | Yes | Jeff Dahl | Michael Boone | Mike Somers | OXFD SHAN ZHAN ROBE | 2023-02-03 22:17 | 0.7 | 0 | 0 | 0 | 0 | 0 | 47697 | 47697 | Implementation | 2022-08-12 | 2023-02-03 09:00 | 2024-12-20 | 2026-12-18 17:00 | [8 empty] | 2.05
f1b46ff1-96d9-f011-8544-6045bd060015 | OUAK/5pkRfT/QIXHW/xJTjS6jhI80N0me3BZQBmz5vafe0fHUjs/FTRXZmf8QdlcxhT4ELFLMjRT8DVLcTFrGg== | 2026-05-26 12:58 | 1519 | Migration InfoBlox NIOS to BloxOne DDI Solution. | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O |  | Execution | Yes | Jeff Dahl | Michael Boone | Mike Somers | Augusta, Baltringen, Bencancour, Charleston, Freeport Plan A& B, Henderson, Houston Katy, Lemont, McIntosh, Nigara Falls, Oyster Creek, Pisticci, Plaquemine, Rheinmunster, Roberta, Russellville, St. Gabriel and Stade DE. | 2025-12-15 09:18 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-11-17 | 2025-12-15 17:00 | 2026-06-30 | 2026-06-30 17:00 | [8 empty] | 3.75
21e4098c-75ea-f011-8544-6045bd060015 | 0fGIQhUUIRi5jM1XLYU0SR/TtQLbayLSrcAqUijt85yh5NXEYdoV3s1+ZwXvwYQFuwjevxjAvJKxchoPCZ7FBg== | 2026-06-01 15:26 | 1529 | Skyline | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O | X.CLA.000052 | Execution | Yes | Jeff Dahl | William Smith | Anthony D'Amato | All Olin locations | 2026-01-05 20:32 | 0.02 | 0 | 0 | 1 |  |  |  |  | Implementation | 2026-03-02 | 2026-03-02 06:00 | 2026-11-30 | 2027-08-27 09:00 | [8 empty] | 3.2
6f424ee3-06de-4fcb-a823-b1e0ec12ee77 | T+4RFcmvTsNDvKBK4NI5b0EXxj7lNuTW0X0v/z/+I7l4pEeWIwjyOwKM58/X8VPPPdSP0YS72zNDhsCVCbx/nw== | 2026-06-01 13:04 | 1383 | CMMC 4.1: Network Remediation | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O | 240068 | Execution | No | Jeff Dahl | Michael Boone | David Kellar | Winchester locations | 2025-04-11 21:11 | 0.66 | 0 | 2 | 3 |  |  |  |  | Implementation | 2025-04-30 | 2025-04-11 09:00 | 2025-11-30 | 2026-09-04 17:00
ac7558a3-020b-4001-8499-c2897d5db5f6 | OZhPy32g39lGBBSwOwsi/V+D55gEtc3ikk9RgSoRD/uxg9mE14Y2/XqSMk7PSy+Wu/U0Si0Twamxoe6FELslqQ== | 2026-03-23 19:05 | 1500 | EALT/OXFD Azure Gov Migration & End-of-Service Hardware Refresh | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O |  | Execution | No | Brian Courtney | Mike Somers | David Kellar |  | 2025-09-15 17:03 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-07-01 | 2025-07-01 | 2025-12-01 | 2025-12-01 09:00
0c674f9c-b327-4896-a222-cc8cc9438cfc | yt5bU7w2HZqdyC1XlBQ+ZNSnBwYiTv/0pClnyyXAKtHE98Z9wYSfVlXpEM82Xj3Zy0T6ePthby9CTUsmJEBgaA== | 2026-06-01 13:11 | 1126 | Telephone Replacement | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O | I.CLA.000040 | Execution | Yes | Jeff Dahl | Michael Boone | Mike Somers | MCIN, PLAQ, PLAQC, LEMT, DNGV, RUSS, CHAS, FMRO, FPLJ, OYST, FREEA, FREEB, MILA, PIST, TERN, RHEI | 2023-02-03 22:12 | 0.87 | 0 | 1 | 0 | 199043 | 199043 | 12938 | 12938 | Implementation | 2023-01-03 | 2023-02-03 09:00 | 2026-12-18 | 2026-12-18 17:00 |  |  |  | N/A |  |  |  |  | 3.75
f968c055-b42c-454b-a8ed-edac8d57b948 | mhucXcXBCD5ZmWxIGrW2veVX9tpnZPs+Ybirus8o99M5ZxX7mNiOkPYQI+xZ8+cwnA4TPwGr13s/c/JVuXIYyg== | 2026-04-10 18:39 | 1499 | CMMC 3.1 & 8.1: Application OS Upgrade Remediation (Blueprint 360) | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | I&O |  | Execution | Yes | Seth Aldrich | Mike Somers | David Kellar | Winchester locations | 2025-09-15 16:57 | 0.77 | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-09-22 | 2025-09-22 | 2025-12-01 | 2026-05-22 17:00 | [9 empty] | .
e20c94d6-a45a-4ca6-b840-ee7f5950595a | 6QIhGwMAX8tCIVpQQU8EQ0LDU80MTPNHcy/VPBsSET2UOfAU3ugk8KljJhcVA+UMl7espE3B8gs09tFgSDBSew== | 2026-05-04 20:14 | 1386 | CMMC 2.8: Olinammo.com SN to FedRamp | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟡 At Risk | 🟢 On Track | 🟢 On Track | I&O | 240068 | Execution | No | Michelle Kissell | Mike Somers | David Kellar | LCAAP | 2025-04-22 15:43 | 0.88 | 0 | 0 | 1 |  |  |  |  | Implementation | 2025-04-28 | 2025-04-30 09:00 | 2026-04-30 | 2026-02-27 17:00 | [9 empty] | .
1c546765-4293-f011-b4cc-000d3a58fbd0 | qv6/lQE8V7y5s9pCnoKYYyUf6c4d2j+9UCxZXgpw4oHh75mS5O7CId4UbRYxIUdTDBIGhBhX18W/sX7SfK5tOQ== | 2026-03-27 20:44 | 1501 | IT Financial Integration | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | ITSBO |  | Execution | Yes | Seth Aldrich | Darlene Schumer | Greg Rutherford | Corporate IT. IT Procurement | 2025-09-16 21:17 | 0.49 | 0 | 0 | 0 |  |  |  |  | Discovery | 2025-10-12 | 2025-10-13 | 2025-12-12 | 2026-05-29 17:00 | [8 empty] | 1.6 | .
5a8cdaf1-beba-401a-bc8e-e3bbda4af62c | mQw2g0yUpUOWNMpZ5+1QO9vzQC7dfec+e19cIPFA5ufr1kS1mm+GPYx9KLQItozfk/jRpENALsiRT2cvp4imow== | 2026-06-04 15:10 | 1366 | CMMC 3.1 & 8.1: Blueprint 360 (Config Mgmt/Risk Assessment) | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | ITSBO |  | Execution | Yes | Seth Aldrich | Darlene Schumer | Greg Rutherford | Corporate | 2024-11-18 19:09 | 0.95 | 0 | 1 | 2 |  |  |  |  | Implementation | 2025-01-24 | 2025-01-13 06:00 | 2025-07-31 | 2026-11-27 17:00 | [9 empty] | .
5d43de4f-ff92-42bc-a44d-f9b2e10579ec | iUtuhBagJdmp/5fhbnVGqTp9vR5B/2klTSy4Pz0Zj+BGIoxWArZQfT9Ui2Kn9UFeFfkKPrX+3TNoC6TFybqjRg== | 2026-06-02 13:22 | 1546 | Ideation to Execution | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | ITSBO |  | Execution | No | Brian Courtney | Brian Courtney | Greg Rutherford | Global | 2026-05-19 18:00 |  | 0 | 0 | 0 |  |  |  |  | Discovery | 2026-05-28 | 2026-05-28 05:00 | 2026-09-25 |  |  |  | ARB Required | Simple Solution | Work Council Not Required |  | AI CoE Not Required
1cc23cd0-f98f-ef11-ac21-000d3a3161c7 | FV2SMTFzdbhqW/SnXtQZIyPhGyvejPJ7KFqBNCI4tWj2QYznlwcV4QgfASQMADUeLms2up1L+13PqEN8fbXshQ== | 2024-10-22 02:33 | 1344 | Documentum High Availability | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Jeff Brantley | Global | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-01-01 | 2024-10-21 16:00 | 2024-07-01 | [9 empty] | 123
1dc23cd0-f98f-ef11-ac21-000d3a3161c7 | 13q92vY2Z5/PdUO6zLzHCCTBY0CEKMk4yFOU/NfYWH59q71or1ugSG2W7R9zLCta+y3uRosfZldMXuXrmY5k9w== | 2024-10-22 02:33 | 1343 | Update dashboards, reports, and alerts related to LIMS systems upgrades | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Jeff Brantley | Global | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-01-01 | 2024-10-21 16:00 | 2024-07-01 | [9 empty] | 123
25c23cd0-f98f-ef11-ac21-000d3a3161c7 | vX4MQlyUrMnnwjZUP+H4j/Y9QNa6K2SmGnW1OtLxQn4z/NNvEQKQSIHtrzB+D0BWpJlhQFmGW34HZeDln/8Gag== | 2024-10-22 02:33 | 1346 | Retire WebTop from Documentum Systems | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Jeff Brantley | North America | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-01-01 | 2024-10-21 16:00 | 2024-12-01 | [9 empty] | 123
4fc23cd0-f98f-ef11-ac21-000d3a3161c7 | qu5W9uUn0doIVD1Q9aDVqRUtAeJhzsLJvPE5fJyVOZgvnoO7m5qosjEOL9La22DQFhUu4UjDMZvS+IA2GNi7zg== | 2025-01-16 06:09 | 1350 | Upgrade IP21 application to latest version | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Jeff Brantley | Global; | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-02-01 | 2024-10-21 16:00 | 2024-11-01 | 2024-10-21 16:00 | [8 empty] | 123
6cc23cd0-f98f-ef11-ac21-000d3a3161c7 | ovFguGLp844b4v0WeVR3PWn0Inm0LQgfnR2LvIixsfBSgibNvoGDje4YENMEaW0hfAtWcVqVUkoqqcXn67IFMw== | 2024-10-22 02:33 | 1354 | Documentum Cloud Modernization | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Jeff Brantley | Global | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-03-01 | 2024-10-21 16:00 | 2024-12-01 | [9 empty] | 123
9ec23cd0-f98f-ef11-ac21-000d3a3161c7 | rnzbh4ru6V0elS4i8p6KzSu6WYW1FyB9e/URQgfT/G0gtH+5ZA+0hycOso6Yx8F0dljZP8vkx4T+XXoQvtxA4g== | 2024-10-22 02:34 | 1359 | Documentum OlinWC Software Enhancements | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Jeff Brantley | Global | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-01-01 | 2024-10-21 16:00 | 2025-01-01 | [9 empty] | 123
1489ddee-9889-f011-b4cb-000d3a356313 | nS02NfRldwZqWBaHoOiLRh6YK6bxBa9zGZa43kqqTW7lrlolpmKzKjZQXQ/mDi7u3rWUZaOHoqeSM4Cdl0AWuA== | 2026-04-22 20:03 | 1418 | GPI Workstation Upgrades |  | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Chris Culberson | Global | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2025-03-01 | 2025-09-04 16:00 | 2026-01-01 | [9 empty] | 123
52f85501-9989-f011-b4cb-000d3a356313 | X0r0syYKIRr06VZew9HxiJEyMDsxrTVJQVuzCaPdZKw5xmW1N65udzgZpquLBJgTj1LTaYaxG9PgwVA3+T+PPA== | 2026-02-26 19:13 | 1459 | Move PCMS from on-prem to SaaS | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Chris Culberson | Global | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2025-03-01 | 2025-09-04 16:00 | 2025-12-01 | [9 empty] | 123
a5163ecd-f98f-ef11-ac21-000d3a3ae441 | YEHxQ3dD/ArumngN1gy6YvC298zlyYoFEq+34FJ+T3yxWai13mRN8dilycIYIV0NBvHVcBbxoVySbkv6RMdxCQ== | 2024-10-22 02:34 | 1356 | Upgrade the M&E IT SolarWinds environment | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Jeff Brantley | Global | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-01-01 | 2024-10-21 16:00 | 2024-07-01 | [9 empty] | 123
3cac53f8-9889-f011-b4cb-00224802cf58 | P0bWwNCRjdw3wQmyo2rpnYLe+6ylJPyRfq1tVUyAoeJSab3vupPVvENNcT0ILnjbaIB6YnB1EFqeT0CnT0zMMQ== | 2025-10-06 15:27 | 1439 | Implement OpenTelemetry based monitoring for the LIMS environment | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Chris Culberson | NA | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2025-03-01 | 2025-09-04 16:00 | 2025-12-01 | [9 empty] | 123
5eac53f8-9889-f011-b4cb-00224802cf58 | C1fyNIza4qQnQDIo/bZ/jHyWOe5k7Zy+IpuFLZr3LDnjO+hhaWgaPEXdvTZouWyItifSrSjFhFLcYbJPIS4dtQ== | 2026-02-26 19:09 | 1444 | Pilot Azure Data Analysis and ML/AI tools | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Chris Culberson | NA | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2025-06-01 | 2025-09-04 16:00 | 2025-12-01 | [9 empty] | 123
e2f3a2cc-f98f-ef11-ac21-002248080eef | TVRLsk9iGL5Byl/+uryvpCymRsRmsCHBiIHcz67UOeysXAS6gguNB2QV7XjSso7G/ZUlTd0c5megCTrsHDoGmg== | 2025-04-22 10:38 | 1341 | Add more plants to Prometheus APM | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Jeff Brantley | North America;EMEAI | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-03-01 | 2024-10-21 16:00 | 2024-11-01 | 2024-10-21 16:00 | [8 empty] | 123
96efbaa2-5d09-4f62-936d-468477372629 | fiPSxFDC1MNuRm368w6o8dk9VTWqtWjKvFwzD60atM3+wG6ImPAScN5IaaI7KEHGGgPRrxEdt5CuHdOBQWGFPw== | 2026-02-26 19:10 | 1508 | Lab instrument PC migration from hybrid deployment to Entra ID | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Heath Corbett | Chris Culberson | All CAPV, GCO, and Epoxy manufacturing locations | 2025-10-07 23:03 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-04-01 | 2025-10-07 14:00 | 2026-12-01
ee5ca6c4-0067-4ee8-8e45-57e8a4082af0 | xkqYQb1mftsbpDNPaiblhVtEykfuHvpgSCPb/sU+6QJNSuz+LROKyH5MTOiPREqZdp5guzpt1TGCKZOWu34gjg== | 2025-10-13 15:44 | 1509 | SmartPlant migration on ProLytX cloud | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Chris Culberson | US | 2025-10-07 23:07 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-01-01 | 2025-10-07 14:00 | 2026-07-01
1f80c2e7-853e-f111-88b4-6045bd0503da | HA/DE2m0HoztdLBsAIyWsCkvvjrGSWqu/8sn4h9NE5I7xF3ZpCg9Vk/oly9zYyCNVqPd5TejE0DS1bLrDO/orQ== | 2026-04-23 18:32 | 1540 | GPI Workstation Refresh | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | Nena Fremin | Nena Fremin | Rebecca MacDonald | U.S. and Germany | 2026-04-22 20:01 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-05-21 | 2026-04-22 16:00 | 2026-11-15 | 2026-04-22 16:00 | [6 empty] | AI CoE Not Required | 4/23 - - Initial Start evaluating options to move forward. (Action: discussion with Austin,Ray,Andy) - Will need to determine how these were originally purchased/leased. | 1.81
edd941ed-9889-f011-b4cc-6045bd060015 | T0+6r1E5ePgNGYSJziPiZEswk0bjSBlg+FFA4zyZG/w3oh/IJ3kXCzdRlaMOl5Bowbuu4FddpgfbvmrVn3I4vw== | 2026-02-26 19:10 | 1423 | Level 3 to/from Level 2 communication - CyberSecurity | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Nena Fremin | Chris Culberson | Global | 2025-09-04 14:11 |  | 0 | 0 | 0 | [6 empty] | 2025-09-04 16:00 | [10 empty] | 123
927f1c48-7e5f-f111-a826-70a8a5afc2af | TIbrnKEMRi+p70P2SzYkh/Lkhhy3X8ef19RTX/fbkmLsmycWnB5dcCctthyOJ/5ApkpFG6e3SJ6UDltXvX1PZA== | 2026-06-03 20:08 | 1548 | Quetech - Day in the Life of | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | Nena Fremin | Nena Fremin | Michael Laflin | North America | 2026-06-03 18:59 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-07-02 | 2026-06-03 16:00 | 2026-07-31 | 2026-06-03 16:00 | [8 empty] | 2.46
a3592d54-118e-4e0b-8f9f-b10a71682b82 | u5danAgGmRLmGpD/exm4ArRXZRJl8I+0CYAjkQlUd9L7xWBOE0L77n5aWRUyF676EuT2b4dkpiFxEK0eQ9VsYQ== | 2026-02-26 19:10 | 1507 | IMDB Feature Enhancements and integration with Olin Applications | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Chris Fox | Chris Culberson | Global | 2025-10-07 22:59 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-02-01 | 2025-10-07 14:00 | 2026-12-31
55f85501-9989-f011-b4cb-000d3a356313 | EuP4TChHTHOgDkgHvhqPkg03uEr5cqeEdB6wVxT6ZymP7JF8D2pQkzxxLf6rSMEjDQag4wVJa8oK0Ya205Xu6w== | 2025-10-06 15:26 | 1460 | ePAS Safe Work Permit Implementation | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake |  | # ITSBO PPM360 PWAService | Felim Larkin | Chris Culberson | US | 2025-09-04 14:11 |  | 0 | 0 | 0 | [6 empty] | 2025-09-04 16:00 | [10 empty] | 123
c9a66504-9989-f011-b4cb-00224802cf58 | Cnm1zroEjtRRIy69HE5/qPQ1xUeS9EsQ1GkHUw/iindFGL7FN4+VUjEUanYh6zbd+hXrQId9n4QuU2QwfJjPyA== | 2025-10-06 15:27 | 1469 | NWA Quality Analyst upgrade or Focus EMI implementation | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake |  | # ITSBO PPM360 PWAService | Heath Corbett | Timothy Baker | TBD | 2025-09-04 14:11 |  | 0 | 0 | 0 | [6 empty] | 2025-09-04 16:00 | [10 empty] | 123
44e9620a-9989-f011-b4cb-00224802cf58 | 4LJHmdW0M2gs3cMkRywQJIPRBvEhmmJ1tEeQvtb57HOqAcRQOh+62MP1kdC0R0zhoFBZRgIc8v7VFLUsI2lxww== | 2025-10-06 15:27 | 1476 | LIMS Implementation at Freeport Cl5 | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake |  | # ITSBO PPM360 PWAService | Heath Corbett | Timothy Baker | Freeport | 2025-09-04 14:11 |  | 0 | 0 | 0 | [6 empty] | 2025-09-04 16:00 | [10 empty] | 123
84d0bc07-9989-f011-b4cc-6045bd060015 | 5BTrkaPVr3kd24prqp/9uHDnpT8KQUO2AG8uUJNEmYK6sndUTu14uECw38DRwOT1TszPIIL654Mtuo+yeNKLVA== | 2025-10-06 15:28 | 1478 | Laboratory gas chromatography (GC) ML-based data analysis implementation | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Intake |  | # ITSBO PPM360 PWAService | Heath Corbett | Timothy Baker | TBD | 2025-09-04 14:11 |  | 0 | 0 | 0 | [6 empty] | 2025-09-04 16:00 | [10 empty] | 123
bdc23cd0-f98f-ef11-ac21-000d3a3161c7 | /UXLUjVaC3nahi141PlUeUX0XEkn2tN2Z42K6/UkULm0+z6lIyrmkBfpbFWXT5fFPiCZkWj/ut/+yZO+iL+V5A== | 2026-05-01 17:01 | 1360 | Lab PC OS & HDW upgrade | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟡 At Risk | 🟢 On Track | 🟢 On Track | M&E | I.CLA.000027 | Execution | No | Brian Courtney | Heath Corbett | Chris Culberson | Global | 2024-10-21 22:14 |  | 0 | 0 | 1 |  |  |  |  | Implementation | 2025-04-01 | 2025-04-01 | 2026-02-27 | 2026-06-30 17:00 | [8 empty] | 123 | Timeline push to 6/30 Additional funding for software
91f85501-9989-f011-b4cb-000d3a356313 | FdF8GpZzFCFI5l1L6QOUgqKUgPoDMXtO/g5sKTM+PVqvG9kkQziGMjpb8N+uuyuP/7ULX/ztz32Dnr491MJXwg== | 2026-05-29 13:09 | 1471 | ShiftConnector GO Implementation | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Execution | No | Brian Courtney | Felim Larkin | Bruce Raiff | Rheinmuenster | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2026-05-01 | 2026-05-01 05:00 | 2026-12-31 |  |  |  | ARB Not Required | Simple Solution | Work Council Required | Submitted to work council and pending approval. With the new hardware(tablets) will need to notify. | AI CoE Not Required | Tablets for shiftconnector - may also be looking to utilize for other business applications. Do we want to limit only to shiftconnector or okay to implement like Freeport. Planning to utilize the Netscope solution to limit access. Will be utilizing 10in standard tablets, will not need to do additional testing for existing 12in tablet. (team okay with this approach). For 5G cellular service will need to engage with regional vendor (TMoble) and be purchased from Plant (IT does not fund outside US). Likely managed by procurement. Equipment - Regional Purchase cannot lease these and required to purchase Dell EU. Transaction is handled in region. Will be in process areas. | 123
60a2eb61-82a4-f011-bbd2-000d3a36e98c | DlZo+cv0eZxPVD+6YCysUYtrVhJFlUyHuQYebZpHVmKmRryztTGeQlaIdvkPFhfdLRLxFLy9UmtVhrvQQ/dhBw== | 2026-05-01 14:42 | 1511 | Control Room KPI Dashboards | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Execution | No | Brian Courtney | Nena Fremin | Michael Laflin | Global manufacturing | 2025-10-08 20:07 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-11-06 | 2025-11-06 06:00 | 2026-04-30 | 2025-11-06 06:00 | [8 empty] | 3.2
f6f3a2cc-f98f-ef11-ac21-002248080eef | P1BWJOfN5r/86ek6Npmb8y2aHBsJx4hzJd203/D7tZO5H3cLtLso6haJ0/gvSFHnrbL3P+zAzqvW+7U8qAfZ+w== | 2026-05-01 16:59 | 1342 | Splunk Upgrade | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track |  | M&E |  | Execution | No | Brian Courtney | Heath Corbett | Chris Culberson | Global | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2025-11-03 | 2025-12-01 06:00 | 2026-04-30 | 2026-05-28 17:00 | [8 empty] | 123
06ff1d64-f331-ee11-bdf3-002248081003 | dLD5bwj4gUtSP6x5DJiYm5Zvmsm8lA58bTOaOBreHhxNQlrgs5yzZuhLbiyWvX5qwqLKSIPDzBfy+OrMNcwIKg== | 2026-05-27 19:47 | 1231 | OpenLab EZChrom to OpenLab CDS Migration | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E | I.CLA.000024 | Execution | No | Brian Courtney | Heath Corbett | Timothy Baker | FREE, STAD, ANGL, BECA, PLAQ | 2023-08-03 11:47 | 0.03 | 0 | 0 | 5 |  |  |  |  | Implementation | 2024-01-01 | 2024-01-01 06:00 | 2024-08-01 | 2026-04-30 17:00 | [8 empty] | 2.76
c8429f66-9e31-4864-9052-01519978b074 | g5DQ7ssNIpq56kRyOcsLUuBRerIBvkoTMeXOc+gsNa6t933LRWehFUl91ZBTDj/HLDq/EX6qtExffycHXofK2Q== | 2026-05-01 12:57 | 1169 | 2025 LIMS Dashboard Deployments (phase 2) | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Execution | No | Brian Courtney | Heath Corbett | Chris Culberson | Freeport, Plaq, Stad, Rhein, Balt, Pist, Zhang, Guaruja, Roberta, Bec, Gumi | 2023-03-14 22:05 | 0.99 | 0 | 0 | 3 |  |  |  |  | Implementation | 2023-01-02 | 2023-01-02 06:00 | 2023-12-29 | 2026-12-31 09:00 | [8 empty] | 3.35
4c142029-b4c7-4455-af48-13d580d4fde6 | gWC/54q+WYPyZfrNaYAG1GYbURZpG5fE2R3MKMT6FOlhcAJixLO8fDFmMERhwDu52/eAT7/OBLuCezuukjnQvQ== | 2026-05-29 12:53 | 1396 | R2 Electrolyzer Optimization | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Execution | No | Brian Courtney | Christopher Rudy | Steven Tanner | Freeport Plants | 2025-06-20 16:32 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-08-04 | 2025-08-04 | 2026-03-31 | 2026-03-31 09:00
cea93ce2-5e7a-ee11-8179-6045bd03b718 | fcCITDusUu9ZRwYftSJWgGtu2pmhKrgAcElgChRkDPsd1HbChuNuJXUlAMaWCHjWgp4Qut54Ru0eRrZYIiXBnQ== | 2026-05-29 13:10 | 1241 | Convert OSI PI to IP21 | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E | X.CLA.000026 | Execution | No | Brian Courtney | Elliot Ibarra | Chris Culberson | Heritage Olin (AUG,BECA,CHAS,HEND,MCIN,NIAG,SGAB) | 2023-11-03 15:38 | 0.07 | 0 | 0 | 0 |  |  |  |  | Implementation | 2024-01-01 | 2024-01-01 06:00 | 2026-06-01 | 2026-06-01 17:00 | [8 empty] | 3.4
c18eb801-9989-f011-b4cc-6045bd060015 | q7pYKNwTjK3y2RtSKIUfwz/Es3efvOOsfSMzoSwFKjuxe3/vYyL9ZKNxEI0mM4vCbxd4OWMf8LHc7pZnVNUV9w== | 2026-06-02 13:22 | 1467 | Sphera Essential Upgrade/Replacement | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E |  | Execution |  | Felim Larkin | Felim Larkin | Tracy Woodall | US - Freeport | 2025-09-04 14:11 |  | 0 | 0 | 0 | [5 empty] | 2026-09-01 | 2025-09-04 16:00 | 2027-10-30 | 2027-10-29 17:00 |  |  | ARB Required | Simple Solution | Work Council Not Required | Freeport only | AI CoE Not Required | Funding License this year 2026 from IT. Services will be funded from business will need our CAR. LeanIX Survey is in process | 123
70de6ca8-5a8c-4926-bd67-d68367965172 | dBeYpOiy2hgCcTbvzqcbf5uwvTxi79PSacSt0Mb5v4Ito7OLpqH9sjKrcfQ/4Fz1t9POIAD6xAbbPj3tLl6L0g== | 2026-05-29 12:53 | 1392 | Global Prometheus APM Rollout | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | M&E | X.CLA.000042 | Execution | No | Brian Courtney | Christopher Rudy | James Barrington | Chemical Plants Globally | 2025-05-15 16:23 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-06-13 | 2025-05-15 09:00 | 2026-07-31 | 2026-07-31 17:00
046aa031-f23f-424c-a8af-5aae6427d0eb | xnG/9PDLPJ+4SKTeQjNZoXjy+tfCLzho3J65QYv9KYxRr9f5HfoFUv8/wo+S/yOf1iBkN0scs5awFtRuK6H32g== | 2026-04-24 19:44 | 1543 | San Bernadino Camera System | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Intake Gate Approval | No | Brian Courtney | # Dickenson, Cory MANI | # Bailey, Dennis WINCH | San Bernadino | 2026-04-24 19:41 |  | 0 | 0 | 0 |  |  |  |  | Implementation |  | 2026-04-24 14:00
8dc23cd0-f98f-ef11-ac21-000d3a3161c7 | iwj3Zfs5Z2neW/FeGrZdWHIzgjUohCc9siG+mkCwcLOO/Yrpemsxbk9ph0Y1yRaHSgLT+NNgsDoxCfvcmJtlfw== | 2025-10-13 15:46 | 1357 | Radford AA IT RFP | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Lisa Humphreys | Dennis Bailey | North America | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2026-01-01 | 2024-10-21 16:00 | 2026-12-31 | [9 empty] | 123
8a0b423d-fcbf-f011-bbd3-00224802cf58 | Fi7ITRfdVDDaMHWEWbAXf6JNJXwzYV8AJCL5FmvVYu9aRjCtOzGmkheCZxyg+nATIpFZARoTRcmpjex0mruYEw== | 2026-03-30 17:59 | 1515 | Winchester Transportation Management | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Intake Gate 2 | No | Raghu Garine | Raghu Garine | # Bailey, Dennis WINCH | EALT, OXFD, WF | 2025-11-12 19:18 | 0 | 0 | 0 | 0 |  |  |  |  | Discovery | 2025-12-11 | 2025-11-12 17:00 | 2026-03-31 | 2025-11-12 17:00 | [8 empty] | 2.7
3d399bd2-f98f-ef11-ac21-002248080eef | 3IXKW0vLEz6mqhtyolE+ixA1z+V71rgTuilsNmJd9Xb750s8KEDDo0CTOXVwP+C/gMFP/2I0KpzfNVKctlAf6g== | 2025-03-03 16:49 | 1361 | SAC Upgrade | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Intake Gate 2 | No | # ITSBO PPM360 PWAService | Steve Holt | Dennis Bailey | North America;EALT, OXFD, E-TECH, Clayton | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-06-01 | 2024-10-21 16:00 | 2024-12-01 | 2024-10-21 16:00 | [8 empty] | 123
59399bd2-f98f-ef11-ac21-002248080eef | 5zrB3KyRQBi/LOJ1Adbl6kEyZrCasjN7ahpo8DoeYK2glX1U4IVe8dwYKR8r4brI38V4eujjEtI4K72XKoQf3Q== | 2024-10-21 22:18 | 1364 | Hyland Replacement - Costpoint AP Processing | Olin 2025 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Lisa Humphreys | Dennis Bailey | North America | 2024-10-21 22:14 |  | 0 | 0 | 0 | [5 empty] | 2024-01-01 | 2024-10-21 16:00 | 2024-07-01 | [9 empty] | 123
afaa178c-e947-f111-bec6-6045bd050c4d | 6bEfcXYPuqa3/0pNlPMusRZ01u4SHovSZU895DtJ2tic1YQkksSPWNMAqTIFWn2z4W0RyNXFk8/8OU2FDP/R1w== | 2026-06-03 17:39 | 1544 | Adept/AutoCad Update | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Intake Gate 2 | No | Brandon Kamp | Brandon Kamp | # Bailey, Dennis WINCH | Winchester - Oxford, East Alton | 2026-05-04 18:46 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-06-09 | 2026-05-04 16:00 | 2026-06-10 | 2026-05-04 16:00 | [8 empty] | 1.4
50811944-5a0a-42d7-a1d1-8dbbc6098ae1 | yaEOIdwxC+we5n2CCe3EYEOla0epMJM0+8qPQMzOzf82dGxK3S3s6UzvFR8Hvh7ymMFiJGOQkdmFoukHg+pFsA== | 2025-11-04 15:21 | 1510 | Project Valiant Radford | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Intake Gate 2 | Yes | # ITSBO PPM360 PWAService | Lisa Humphreys | # Bailey, Dennis WINCH | Winchester | 2025-10-07 23:11 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-07-01 | 2025-10-07 14:00 | 2026-12-31 | 2025-10-07 14:00
c1c26f4e-4cbe-f011-bbd2-000d3a5bdd18 | 8oX2+bA7ZsruL8G8M5MD/x/EErpl+FieP/obbcYHi6eZAtQ0lALTxPCmAaMem2mQYBB1sjOqAJqgas4AhCEXxA== | 2026-06-03 18:31 | 1513 | Sterling EDI to SAP Integration Suite | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Execution | Yes | Michelle Kissell | Brandon Kamp | # Bailey, Dennis WINCH | All Winchester and White Flyer Sites; LCAAP | 2025-11-10 15:46 | 0.57 | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-12-09 | 2025-12-09 06:00 | 2026-11-30 | 2026-11-26 09:00 | [8 empty] | 3.8
5b8a86f1-34d1-f011-bbd3-00224802cf58 | qMm88AcItFuOb7CF9gwrEFvjNMI2Iuo9o3K0PnI+w5GygMfOquxLym08dfv555+JFMvAe2+4BP848MlyLmkPww== | 2026-06-02 13:26 | 1517 | GuiXT Ugrade to LiquidUI | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Execution | No | Bob Cassout | Raghu Garine | # Bailey, Dennis WINCH | EALT, OXFD | 2025-12-04 17:16 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2026-06-01 | 2025-12-04 17:00 | 2026-08-14 | 2025-12-04 17:00 |  |  | ARB Review - Completed | Simple Solution | Work Council Not Required |  | AI CoE Not Required |  | 2.5
a828b209-2063-f011-bec2-00224802cf58 | BlRpZOM8B7iEmrvQJlsvG45MkPFlpGPPzDge8FlZJKDpieyJxTKSvlJsjAcutmaCbk8MGsKBn2uaeNmhfy9v9A== | 2025-12-19 15:59 | 1404 | WIN AUS - Pronto Cloud | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Execution | No | Darlene Schumer | Brandon Kamp | Dennis Bailey | Australia | 2025-07-17 15:10 | 0 | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-08-14 | 2025-08-14 | 2025-12-31 | 2025-09-30 17:00 | [8 empty] | 3.1
b9ff1feb-0025-4088-b98d-23cf493bad18 | m20q2vhuf7250I+7ymOxD1sylZSCZ9tQQOdh1dM6Lxm+o8s9nHjrUGN+X5NnCpDeU6rm7eQxA3w+/vveUcPXgw== | 2025-10-21 19:01 | 1486 | (Hold LCAP) CMMC 2.4: Commercial Cloud Application Inventory | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Execution |  | Darlene Schumer | Dennis Bailey | David Kellar | Winchester locations | 2025-09-08 20:11 |  | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-08-01 | 2025-09-08 09:00 | 2025-12-31 | 2025-12-31 09:00
19fb538f-3713-45ae-8581-3a16fec79fda | fOI0gR2EbiPFn44quw9Ff2ncnwnXcb72nquWoYIGn0/RBK3tn6B0s4EVnsNdmhj0WpC7D7imM7/6mbVdgFH7Hg== | 2026-06-02 18:02 | 1488 | CMMC 4.2: Rewrite/Upgrade Applications on Unsupported Operating Systems | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Execution | Yes | Seth Aldrich | Dennis Bailey | David Kellar | Winchester locations | 2025-09-09 18:59 | 0.69 | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-10-01 | 2025-10-01 | 2025-12-31 | 2026-08-21 17:00 | [9 empty] | .
4ccc1402-4e79-466a-b697-bc48faa58483 | 3vn2SlGW2XtMotoe5AIszX7zn7e6FKEYS6ZdFj1jeiI8udH63n4xsv+ZcNcMJ3Ak3Xm/A/BQKmxYkHMrF6qFtQ== | 2026-04-15 13:08 | 1484 | CMMC 2.1: Infinity QS System & Shared PCs | CMMC Remediation Portfolio | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Execution | Yes | Michelle Kissell | Dennis Bailey | David Kellar | Winchester locations | 2025-09-08 19:55 | 0.38 | 0 | 0 | 0 |  |  |  |  | Implementation | 2025-09-22 | 2025-09-22 | 2026-01-02 | 2026-11-18 17:00 | [9 empty] | .
36f074b1-0076-4b1d-bf22-cc9450c005f5 | S/z8qxWlcuEzcZd/3ZEHk7ziRMO6A9vuKLkgCoAruq5GcMHUmpzDFQdPXfpZwpdU0b6wDw9g9CoyTR6rZTaNZw== | 2026-06-02 18:43 | 1485 | CMMC 2.3: Unmanaged Local Applications | CMMC Remediation Portfolio | Active | 🟡 At Risk | 🟢 On Track | 🟡 At Risk | 🟢 On Track | 🟢 On Track | Winchester |  | Execution | Yes | Michelle Kissell | Dennis Bailey | David Kellar | Winchester locations | 2025-09-08 20:04 | 0.72 | 1 | 0 | 0 | 55000 | 55000 |  |  | Implementation | 2025-08-01 | 2025-08-01 | 2025-11-17 | 2026-01-02 17:00
0751fed7-658e-42f6-ad00-d1634cb056e1 | akIInFIiRwa+pMQq4ZL5dVGCs+sro7DJsV/UeQpr+Wen2rWBaxxWtXe7cnLjNnl1Rm0kkwQqtNQdVhRbQdzbnw== | 2026-06-02 16:42 | 1537 | NeoSystem Environment Migration | Olin 2026 | Active | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | 🟢 On Track | Winchester |  | Execution | Yes | Brian Courtney | Lisa Humphreys | # Bailey, Dennis WINCH | Lake City | 2026-04-08 13:32 | 0.39 | 0 | 0 | 0 |  |  |  |  | Implementation |  | 2026-04-08 14:00 |  | 2026-06-25 14:00 |  |  | ARB Not Required | N/A | Work Council Not Required | N/A | AI CoE Not Required | Update hosting information post implementation in LeanIX

## hiddenSheet (hidden)
msdyn_project:7r+lOd2x0F1RU1BY2PWT9hLXqC4LrL7tHYjVZ+mrs/gBUfR8nY/zmpU/W2CaZlM2j3H7RYEwxWhuak+bg1A2Vg==:msdyn_projectid=%28Do%20Not%20Modify%29%20Project&checksumLogicalName=%28Do%20Not%20Modify%29%20Row%20Checksum&modifiedon=%28Do%20Not%20Modify%29%20Modified%20On&m360_projectid=Project%20ID&msdyn_subject=Name&m360_portfolio=Portfolio&statecode=Project%20Status&m360_overallhealth=Overall%20Health&m360_budgethealth=Budget%20Health&m360_schedulehealth=Schedule%20Health&m360_resourceshealth=Resources%20Health&m360_scopehealth=Scope%20Health&m360_itdepartment=IT%20Department&m360_cpmsprojectnumber=CPMS%20Project%20Number&m360_currentstagename=Current%20Stage%20Name&m360_itpmrequested=IT%20PM%20Requested&ownerid=Project%20Manager&m360_requestor=Requestor&m360_businesssponsorchampion=Business%20Sponsor%20%2f%20Champion&m360_locationsimpacted=Locations%20Impacted&createdon=Created%20On&msdyn_progress=%25%20Complete&proj_activechanges=Active%20Changes&proj_activeissues=Active%20Issues&proj_activerisks=Active%20Risks&m360_actualcapex=Actual%20CAPEX&m360_actualcapex_base=Actual%20CAPEX%20%28Base%29&m360_actualopex=Actual%20OPEX&m360_actualopex_base=Actual%20OPEX%20%28Base%29&proj_projecttype=Project%20Type&m360_plannedinitiativestartdate=Planned%20Initiative%20Start%20Date&msdyn_scheduledstart=Start%20Date&m360_plannedinitiativeenddate=Planned%20Initiative%20End%20Date&msdyn_finish=Finish%20Date&m360_plannedprojectenddate=Planned%20Project%20End%20Date&m360_plannedprojectstartdate=Planned%20Project%20Start%20Date&m360_arbstatus=ARB%20Status&m360_easolution=EA%20Solution&m360_workcouncilstatus=Work%20Council%20Status%20&m360_workcounciloutcome=Work%20Council%20Outcome%20&m360_aicoestatus=AI%20CoE%20Status&m360_intakenotes=Intake%20Notes&m360_intakescore=Intake%20Score%20&m360_gtgplan=GTG%20Plan
Active | Inactive
🟢 On Track | 🟡 At Risk | 🔴 Off Track
🟢 On Track | 🟡 At Risk | 🔴 Off Track
🟢 On Track | 🟡 At Risk | 🔴 Off Track
🟢 On Track | 🟡 At Risk | 🔴 Off Track
🟢 On Track | 🟡 At Risk | 🔴 Off Track
Ent Solutions | GIS | HR | I&O | ITSBO | M&E | Winchester
Yes | No
Implementation | Discovery
ARB Required | ARB Not Required | ARB Review - In Progress | ARB Review - Conditional Approval | ARB Review - Completed | ARB Review – Denied
Simple Solution | Complex Solution | N/A
Work Council Required | Work Council Not Required | Work Council Review - In Progress | Work Council Review - Completed | Work Council Review - With Restrictions
AI CoE Required | AI CoE Not Required | AI CoE Review - In Progress | AI CoE Review - Completed